## Contents
SCHEDULING WITH A SPREADSHEET
TABLE OF CONTENTS
Section
Introduction
1 | Capacity Planning vs Finite Scheduling - the essential difference
2 | Time cascades downwards
3 | Re-sequencing the schedule
4 | A Simple Gantt Chart
5 | Setting up a Calendar
6 | Calculation of Job Stop Time Through the Calendar
7 | Julian Dates
8 | Setting up a Julian Calendar
9 | Using the Calendar Formulas
10 | Multiple Machines or Work Centres
11 | Joining Text Together and Indirect References
12 | Separate Calendars for each Work Centre
13 | Repetitive Production and Setups
14 | A Set-up Matrix
15 | Applying the Set-up Matrix Formula
16 | Gantt Chart 2 - Hours per Day
17 | Gantt Chart 3 - Units per Day
18 | Working Hours Between Two Dates (Calendar Formula 2)
19 | Applying Calendar Formula 2
20 | Jobs That Pass Through Multiple Work Centres
21 | Repetitive Production that Passes Through Multiple Work Centres
22 | Transfer Batches
23 | Re-Using Parts of the Calendar Formulas
24 | Repetitive Production Through Multiple Work Centres, With Calendars
25 | A Pull Schedule
26 | Push and Pull Schedule
27 | Working Backwards Through a Calendar (Calendar Formula 3)
28 | Applying Calendar Formula 3 to a Pull Schedule
29 | Multiple Work Centre - Pull Schedule
30 | Repetitive Production Through Multiple Work Centres - Pull Schedule
31 | Repetitive Production, Multiple Work Centres, Pull Schedule, With Calendars
32 | Push Pull Push - 3 Pass Logic
33 | Multiple Work Centre - 3 Pass Schedule
34 | Repetitive Production Through Multiple Work Centres - 3 Pass Schedule
35 | 3 Pass Schedule With a Calendar
36 | 3 Pass Schedule With Multiple Calendars
37 | Repetitive Production, 3 Pass Schedule With Multiple Calendars
38 | Project Scheduling
39 | Critical Path Analysis
40 | Make-to-Stock (Inventory) Schedule
41 | Make-to-Stock Logic Explained
42 | Make-to-Stock Schedule - Formulas Explained
43 | Inventory Cover Calculation
To Come:
Project scheduling with finite resources
Material Requirements to Support a Schedule

## Introduction
Introduction
For years spreadsheets have been used to design and prototype scheduling systems. They have now grown up, and are being used to develop serious production scheduling applications.
Who Should Use This Tutorial
This tutorial is aimed at spreadsheet literate people who are involved in planning and scheduling production activities. The techniques and formulas set out in this tutorial are being used by manufacturing companies daily; this is a practical, not an academic, exercise.
Background to Scheduling With a Spreadsheet
We have been designing, building and implementing production scheduling systems for manufacturing companies for over 10 years. When PC's and spreadsheets were less capable than they are now, we used spreadsheets to design and prototype scheduling algorithms, and to train on some of the principles of scheduling. Prototype designs were then handed over to software developers to write in more resilient and efficient programming languages.
Often the pressure was on to throw several thousand records of data at the prototypes and use them for live scheduling, before handing them over to the software developers. So, in order to 'shoehorn' a big scheduling task into a small PC, we recorded macro's that wrote a formula, copied it down, overwrote the cells with values, then moved on to the next column, so that no memory consuming live formulas were left behind. Typically, most of the macro code prepared downloaded data for scheduling, and generated reports from the schedule, with only a small portion of the macro calculating the schedule itself. We ended up with big cumbersome macro driven scheduling systems that ordinary, spreadsheet literate people were locked out of.
Thankfully we now have Pentium II's and III's which allow us to apply formulas to large amounts of data, and we have features such as Excel's PivotTable which will re-arrange and summarise data for scheduling, and prepare reports without resorting to writing macros. It makes the job, of building a scheduling system with a spreadsheet, a whole lot easier, and within the capability of the average speadsheet user.
Build Your Own System
Our offering to our clients has now changed, and we can now give them the option of either building a scheduling system for them, or teaching their staff to build one for themselves, and providing guidence while they do it.
Interface to Your ERP System
Our clients include companies such as Shell, Toyota and Unilever, as well as many smaller manufacturing concerns. They all have ERP or older MRPII systems, and have felt that the functionality of their systems need to be extended to give them the kind of responsive scheduling they are looking for. Spreadsheet based scheduling applications have been interfaced to SAP, Baan and many other ERP systems.
Structured and Disciplined Approach
Spreadsheets have earned themselves a bad reputation amongst software purists, because they can, and often are, used in an unstructured way. Building a scheduling system requires a structured and disciplined approach. Please resist the trap, that many fall into, by creating a table on a single worksheet that looks like the report that you want to see. The approach used here is to create lists in the form of databases, with a heading at the top of each column, and with universal formulas that can be copied and pasted down a column, and work on every row. If all the calculations are done in a structured database, then reports, with sub-totals and charts, can easily be created with a PivotTable.
E-mail Us:
Production-Scheduling@Mweb.co.za

## Section 1
Capacity Planning vs Finite Scheduling - the essential difference
Imagine you have 5 jobs to do before this time tomorrow:
| Jobs | Hours
| job A | 7
| job B | 12
| job C | 4
| job D | 5
| job E | 8
| Total | 36
You have work totalling an estimated 36 hours to complete in a day (24 hours). You have a problem.
Capacity planning tells you that you have a problem by saying that you are (36÷24) 150% loaded
for the day, and leaves you to resolve the problem by adding more resources or negotiating
alternative due dates.
Finite scheduling, on the other hand, recognises that the capacity of the resource is finite, and tells
you that some of the jobs are going to be late, and it can also tell you:
- which jobs are going to be late
- how late they are going to be
- are they important jobs, or for important customers
- what revised delivery dates can be promised
- how all these would change if the Jobs were undertaken in a different sequence
I would argue that compared with capacity planning, finite scheduling gives you richer management
information.

## Section 2
Time cascades downwards
Lets add some additional columns to the list of jobs:
| Jobs | Hours | Start | Stop | Due | On time
| job A | 7 | 0 | 7 | 24 | 1
| job B | 12 | 7 | 19 | 24 | 1
| job C | 4 | 19 | 23 | 24 | 1
| job D | 5 | 23 | 28 | 24 | 0
| job E | 8 | 28 | 36 | 24 | 0
This is now more than a list of jobs, it is a schedule.
Each formula is entered in the top cell of the column and then copied down, take a look at them:
- the first job starts at hour zero
=E7 | - the next job starts when the previous one stops
=D8+C8 | - the stop is the start plus the hours
- each job is due 24 hours from now
=E8<=F8 | - a job is on time if it stops on or before it is due
Double click on a cell containing a formula, and the cells it refers to will be colour coded.
You can see that each job is dependant on the one before it, and time cascades downwards.
You can also see that only three of the five jobs will be on time, but lets see what happens when
we do them in a different sequence.

## Section 3
Re-sequencing the schedule
We will add a sequence column to the left of the table:
| Seq | Jobs | Hours | Start | Stop | Due | On time
| 1 | job A | 7 | 0 | 7 | 24 | 1
| 2 | job C | 4 | 7 | 11 | 24 | 1
| 3 | job D | 5 | 11 | 16 | 24 | 1
| 4 | job E | 8 | 16 | 24 | 24 | 1
| 5 | job B | 12 | 24 | 36 | 24 | 0
If we do job B last, four out of the five jobs will be on time. The table was sorted into a different
sequence by entering the numbers 1 5 2 3 4 down the sequence column, and with the pointer in
the sequence column, clicking on the 'sort ascending' icon.

## Section 4
A Simple Gantt Chart
The start and stop times of each job are calculated by formulas that cascade down the columns, but as a visual aid, the
information may also be displayed as a Gantt chart. This is how you set it up:
- to the right of the schedule make narrow columns and head them from hours 1 to 36
Seq | Jobs | Hours | Start | Stop | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
1 | job A | 7 | 0 | 7 | bar: 1 to 7
2 | job C | 4 | 7 | 11 | bar: 8 to 11
3 | job D | 5 | 11 | 16 | bar: 12 to 16
4 | job E | 8 | 16 | 24 | bar: 17 to 24
5 | job B | 12 | 24 | 36 | bar: 25 to 36
| - enter this formula |  |  |  | 1: =IF(AND(F$8>$D10,F$8<=$E10),1,"")
It tests the cell to see whether the hour number in the column heading is between the start and stop.
If it is, it returns a 1, if not it returns "" (a blank)
The $'s ensure that when the formula is copied it continues to reference columns D and E for the start and stop,
and row 8 for the hour number.
- set Format¦Conditional Formatting¦Pattern¦Colour if the cell value =1, to emphasize the cell with a colour
- copy the formula in F10, and paste it to the range F10:AO14
Try changing the figures in the Hours column to see how the Gantt chart responds, or change one of the sequence numbers
and sort to re-sequence the schedule.

## Section 5
Setting up a Calendar
So far we have assumed that the work centre works 24 hours a day without a break, as would a continuous process such as
an oil refinery or a paper mill. However, if it is not a continuous process we need to define the working periods during which the
work centre is available. Here is an example of a calendar in hours, and decimals of an hour
(later we will examine dates and times):
Period Number | Begin | End | Working Hours | Working Hours so far (Cum)
1 | 0 | 0 | 0 | 0 | establishes the beginning of the calendar at zero hour, midnight
2 | 8 | 10 | 2 | 2 | work from 8:00 am to 10:00 am
3 | 10.25 | 13 | 2.75 | 4.75 | a 15 min break, resume work at 10:15 am and work till 1:00 pm
4 | 13.5 | 15.5 | 2 | 6.75 | 30 min for lunch, then work till 3:30 pm
5 | 15.75 | 18 | 2.25 | 9 | a 15 min break in the afternoon, then work till 6:00 pm
6 | 19 | 22 | 3 | 12 | an hour for dinner, then work till 10:00 pm
Expressed as 12 hour clock times, the calendar looks like this:
1 | 0:00 | 0:00 | 0 | 0
2 | 8:00 | 10:00 | 2 | 2
3 | 10:15 | 13:00 | 2.75 | 4.75
4 | 13:30 | 15:30 | 2 | 6.75
5 | 15:45 | 18:00 | 2.25 | 9
6 | 19:00 | 22:00 | 3 | 12
We are counting hours into the schedule beginning at midnight.
Each line is a working period, the breaks lie in between.
In this example we begin at 8:00 AM, end at 10:00 PM, work for 12 hours, and have 2 hours of breaks.
Take a look at the formulas, they are very simple.
Now consider this problem:
If you start a 7 hour job at 8:30 AM, at what time will you stop?
You could do this:
| Begin | End | Duration
| 8.5 | 10 | 1.5
| 10.25 | 13 | 2.75
| 13.5 | 15.5 | 2
| 15.75 | 16.5 | 0.75
| Total |  | 7
With a bit of trial and error you can work out that the answer is at hour 16.5 or 4:30 pm
However, a more comprehensive calculation is set out on the next worksheet.

## Section 6
Calculation of Job Stop Time Through the Calendar
This gets complex, so you can skip this part if you wish and just accept that the forulae work when you apply them, or you can
persevere and understand how the formulas work. The start of the job could be within a working period, or it could fall between two
working periods. Here is the calendar again:
Period Number | Begin | End | Working Hours | Working Hours so far (Cum)
1 | 0 | 0 | 0 | 0
2 | 8 | 10 | 2 | 2 |  | change these figures and work through
3 | 10.25 | 13 | 2.75 | 4.75 |  | the stages of the calculation, to gain
4 | 13.5 | 15.5 | 2 | 6.75 |  | an understanding of the formulas
5 | 15.75 | 18 | 2.25 | 9
6 | 19 | 22 | 3 | 12
|  | Starting a job at: |  | 8.5 | (8:30 AM)
|  | Work for: |  | 7 | hours
Stages of the calculation:
8:30 AM is after period 2 begins | [5 empty] | 2 | =MATCH(E16,B9:B14)
8:30 AM is after period 1 ends | [5 empty] | 1 | =MATCH(E16,C9:C14)
8:30 AM lies between the beginning and end of period 2 | [5 empty] | 2 | =G21+(G21=G22)
period 2 begins at 8:00 AM | [5 empty] | 8 | =INDEX(B9:B14,G23,1)
period 2 ends at 10:00 AM | [5 empty] | 10 | =INDEX(C9:C14,G23,1)
you can start the job at 8:30 AM because it is within a working period | [5 empty] | 8.5 | =MAX(G24,E16)
the number of hours from the start of the job to the next break | [5 empty] | 1.5 | =G25-G26
cum hours at end of period 2 | [5 empty] | 2 | =INDEX(E9:E14,G23,1)
the job starts at cum hour 0.5 of the calendar | [5 empty] | 0.5 | =G28-G27
the job stops at cum hour 7.5 of the calendar | [5 empty] | 7.5 | =G29+E17
the job stops during period 5 | [5 empty] | 5 | =MATCH(G30,E9:E14)+1
period 5 ends 9 working hours into the calendar | [5 empty] | 9 | =INDEX(E9:E14,G31,1)
period 5 ends at hour 18 (6:00 PM) | [5 empty] | 18 | =INDEX(C9:C14,G31,1)
the job will stop 1.5 hours before period 5 ends | [5 empty] | 1.5 | =G32-G30
the job will stop at hour 16.5 (4:30 PM) | [5 empty] | 16.5 | =G33-G34
With a series of substitutions, the 15 formulas can be condensed into 4 as follows:
Calc1 | 2 | =MATCH(E16,B9:B14)+(MATCH(E16,B9:B14)=MATCH(E16,C9:C14))
Calc2 | 0.5 | =INDEX(E9:E14,B39,1)-(INDEX(C9:C14,B39,1)-MAX(INDEX(B9:B14,B39,1),E16))
Calc3 | 5 | =MATCH(B40+E17,E9:E14)+1
Job Stop | 16.5 | =INDEX(C9:C14,B41,1)-INDEX(E9:E14,B41,1)+B40+E17
The meanings of the formulas are:
Calc1 | 8:30 AM lies between the beginning and end of period 2
Calc2 | the job starts at cum hour 0.5 of the calendar
Calc3 | the job stops during period 5
Job Stop | the job will stop at hour 16.5 (4:30 PM)

## Section 7
Julian Dates
It was Julius Caeser who first established the calendar based on 365 days per year with leap years, hence Julian dates. One of the reasons why spreadsheets are so good for scheduling is the way that they handle dates and times. All spreadsheets start counting time in days, and decimals of a day, from midnight before 1st January 1900, and there are enough decimal places of a day to measure time to the nearest 3 thousanth of a second!
This is the date and time according to the system clock in this computer, using the =NOW() function:
| 46231.3078 | days since 1 January 1900
Keep hitting the F9 key to recalculate, and watch the clock change. Add 1 to it and you get the same time tomorrow. The really neat thing is that we only have one unit for measuring time, a day. We don’t have to worry about seconds, minutes, hours, weeks, fortnights, months, quarters, years, decades and centuries. However we can display the date and time in different ways with Format Cells¦Number¦Date and Time.
Here are some different formats of NOW:
46231.3078
46231.3078
46231.3078
2026-07-28 07:23
2026-07-28 07:23
2026-07-28 07:23
2026-07-28 07:23
2026-07-28 07:23
2026-07-28 07:23
2026-07-28 07:23
and by using =TEXT:
Tue
TuesdayTuesday
Jul
J07
2026
Take a look also at the date and time functions.
The spreadsheet takes care of the days in each month, and leap years etc.

## Section 8
Setting up a Julian Calendar
So far we have scheduled using hours, rather than days, to measure short periods of time. Somehow "I have a meeting with a client, it should take about 2 hours" sounds better than "it should take about 0.08333 of a day". We have also pegged "zero hour" at midnight on some arbitrary day, rather than midnight 1 January 1900. But we will need to get used to these ideas if we are going to harness the full power of Julian dates.
Here is a calendar using Julian dates:
these two columns are just for information (note the formula - hours are days x 24)
Hours | Day | Begin | End | Cum Days | Establish the first date as follows:
type =NOW() to put in the current date and time
2 | Mon | 2000-03-13 08:00 | 2000-03-13 10:00 | 0.083333 |  | copy, then Edit¦Paste Special¦Values
2.75 | Mon | 2000-03-13 10:15 | 2000-03-13 13:00 | 0.19792 |  | Format¦Cells¦Number¦Date and choose a format that
2 | Mon | 2000-03-13 13:30 | 2000-03-13 15:30 | 0.28125 |  | shows both the date and time
2.25 | Mon | 2000-03-13 15:45 | 2000-03-13 18:00 | 0.375 |  | edit the date and time
3 | Mon | 2000-03-13 19:00 | 2000-03-13 22:00 | 0.5
2 | Tue | 2000-03-14 08:00 | 2000-03-14 10:00 | 0.58333 | Copy, paste and edit to set up the first day
2.75 | Tue | 2000-03-14 10:15 | 2000-03-14 13:00 | 0.69792
2 | Tue | 2000-03-14 13:30 | 2000-03-14 15:30 | 0.78125 | Add 1 for the other days of the week
2.25 | Tue | 2000-03-14 15:45 | 2000-03-14 18:00 | 0.875
3 | Tue | 2000-03-14 19:00 | 2000-03-14 22:00 | 1
2 | Wed | 2000-03-15 08:00 | 2000-03-15 10:00 | 1.0833
2.75 | Wed | 2000-03-15 10:15 | 2000-03-15 13:00 | 1.1979
2 | Wed | 2000-03-15 13:30 | 2000-03-15 15:30 | 1.2812
2.25 | Wed | 2000-03-15 15:45 | 2000-03-15 18:00 | 1.375
3 | Wed | 2000-03-15 19:00 | 2000-03-15 22:00 | 1.5
2 | Thu | 2000-03-16 08:00 | 2000-03-16 10:00 | 1.5833
2.75 | Thu | 2000-03-16 10:15 | 2000-03-16 13:00 | 1.6979
2 | Thu | 2000-03-16 13:30 | 2000-03-16 15:30 | 1.7812
2.25 | Thu | 2000-03-16 15:45 | 2000-03-16 18:00 | 1.875
3 | Thu | 2000-03-16 19:00 | 2000-03-16 22:00 | 2
2 | Fri | 2000-03-17 08:00 | 2000-03-17 10:00 | 2.0833
2.75 | Fri | 2000-03-17 10:15 | 2000-03-17 13:00 | 2.1979
2 | Fri | 2000-03-17 13:30 | 2000-03-17 15:30 | 2.2812 | We don't plan to work Friday evenings
2.25 | Fri | 2000-03-17 15:45 | 2000-03-17 18:00 | 2.375
2 | Mon | 2000-03-20 08:00 | 2000-03-20 10:00 | 2.4583
2.75 | Mon | 2000-03-20 10:15 | 2000-03-20 13:00 | 2.5729 | Add 7 for the other weeks
2 | Mon | 2000-03-20 13:30 | 2000-03-20 15:30 | 2.6562
2.25 | Mon | 2000-03-20 15:45 | 2000-03-20 18:00 | 2.75
3 | Mon | 2000-03-20 19:00 | 2000-03-20 22:00 | 2.875
A calendar for a live scheduling system may be up to several thousand rows long, so you may wish to replace the formulas with values, after you have set it up, to save on memory and calculation time. You can allow for public holidays by deleting rows, and you can allow for overtime by inserting rows or by extending the working periods.
After deleting or inserting rows, don't forget to copy down the formula in the Cum Days column.
A quick way of copying a formula down to the bottom of the block of data, is to select the top cell, then point to the bottom
right corner of the cell, and when the solid black cross appears, like this: | [6 empty] | double click.
+

## Section 9
Using the Calendar Formulas
The formulas for calculating the job stop time through the calendar, that we developed in section 6, works just as well on days
as it does on hours, so it can be applied to the Julian calendar like this:
| Start of first job: |  |  | 2000-03-14 08:30
Seq | Jobs | Hours | Days | Start | Calc1 | Calc2 | Calc3 | Stop
1 | job A | 7 | 0.29167 | 2000-03-14 08:30 | 7 | 0.52083 | 10 | 2000-03-14 16:30
2 | job C | 4 | 0.16667 | 2000-03-14 16:30 | 10 | 0.8125 | 11 | 2000-03-14 21:30
3 | job D | 5 | 0.20833 | 2000-03-14 21:30 | 11 | 0.97917 | 13 | 2000-03-15 12:45
4 | job E | 8 | 0.33333 | 2000-03-15 12:45 | 13 | 1.1875 | 17 | 2000-03-16 08:30
5 | job B | 12 | 0.5 | 2000-03-16 08:30 | 17 | 1.5208 | 22 | 2000-03-17 08:30
| =C10/24 |  |  | days are hours ÷ 24 - we need to convert to use the Julian calendar
| =IF(I9,I9,E$6) |  |  | if there is a stop time of the previous job, start then, if not use "Start of first job" in E6
| =MATCH(G10+D10,'Section 8'!$E$10:$E$39)+1 |  |  |  |  | the calendar formulas have been explained in Section 6, but note how
the calendar on Section 8 is referenced from from this worksheet
Not only can you reference the calendar if it is on another worksheet, but it can also be in another workbook.
Try this experiment:
- open a new workbook (File¦New¦Workbook)
- make two windows (Window¦Arrage¦Horizontal)
- click on the tab of Section 8 and drag the worksheet into the new workbook
- now look at the calendar formulas, and see how they have "followed" the calendar to its new workbook
- save the new workbook as "Calendar" in another folder on your hard drive, or elsewhere on your network, and close it
- the formulas establish a link to the calendar, which includes the full path to the workbook
- you can confirm this with Edit¦Links
This can be useful if you want several schedules to share the same calendar, but the calculation speed is quicker if the
calendar is in the same workbook.
As with the schedules in Section3 and 4, you can change the hours, or the start of the first job, or the sequence numbers
and sort to re-sequence, and see how the calculations respond.
If you try and start before the calendar begins, or you drop off the end of the calendar, the formulas will return errors.
Formulas:
Start = IF([Stop, row above],[Stop, row above],E6)
Stop = INDEX('Section 8'!$D10:D39,[Calc3],1)-INDEX('Section 8'!$E10:E39,[Calc3],1)+[Calc2]+[Days]

## Section 10
Multiple Machines or Work Centres
So far we have only considered one work centre. For multiple work centres we could create a separate schedule for each,
but here is another way of doing it:
|  | Start of first job: |  |  | 2000-03-14 08:30
W/C | Seq | Jobs | Hours | Days | Start | Calc1 | Calc2 | Calc3 | Stop
1 | 1 | job A | 7 | 0.29167 | 2000-03-14 08:30 | 7 | 0.52083 | 10 | 2000-03-14 16:30
1 | 2 | job C | 4 | 0.16667 | 2000-03-14 16:30 | 10 | 0.8125 | 11 | 2000-03-14 21:30
1 | 3 | job D | 5 | 0.20833 | 2000-03-14 21:30 | 11 | 0.97917 | 13 | 2000-03-15 12:45
2 | 1 | job E | 8 | 0.33333 | 2000-03-14 08:30 | 7 | 0.52083 | 10 | 2000-03-14 17:30
2 | 2 | job B | 12 | 0.5 | 2000-03-14 17:30 | 10 | 0.85417 | 15 | 2000-03-15 17:30
2 | 3 | job F | 6 | 0.25 | 2000-03-15 17:30 | 15 | 1.3542 | 18 | 2000-03-16 10:45
| =IF(A9=A8,J8,F$6) |  |  | if the work centre is the same as the job above, then start when the previous job stops
else use the "Start of first job" in F6
In this example a job can be assigned to Work Centre 1 OR Work Centre 2, and then assigned a sequence within it.
(We shall look one job passing through multiple work centres later)
Note that the 1's and 2's in the Work Centre column are codes rather than numbers, so they have been formatted as text
Format¦Cells¦Number¦Text.
You can now change both the work centre number and the sequence number, and sort with Data¦Sort
- Sort By W/C Ascending
- Then By Seq Ascending
Formulas:
Start = IF([W/C]=[W/C, row above],[Stop, row above],F6)
Stop = INDEX('Section 8'!$D10:D39,[Calc3],1)-INDEX('Section 8'!$E10:E39,[Calc3],1)+[Calc2]+[Days]

## Section 11
Joining Text Together and Indirect References
In Section 12 we will use separate calendars for each work centre, but first we need to understand a couple of techniques:
Joining text together or concatenation
The "+" sign is used to add numbers together, but the "&" sign is used to join text together or join text with numbers, e.g.
| John | Smith | JohnSmith | =B9&C9
this may look better with a space in between:
| John | Smith | John Smith | =B13&" "&C13
it also works with numbers:
| Section | 11 | Section 11 | =B17&" "&C17
Indirect references
999
we can add text together to make something that looks like a cell reference:
| B | 22 | B22 | =B26&C26
to make it behave like a cell reference, add the =INDIRECT function
| B | 22 | 999 | =INDIRECT(B30&C30)
a direct reference to a cell on another worksheet:
|  | A Simple Gantt Chart |  | ='Section 4'!A1
an indirect reference to the same cell:
| Section 4 | #REF! |  | =INDIRECT("'"&B38&"'!A1")

## Section 12
Separate Calendars for each Work Centre
The next two worksheets contain calendars, and the following table assignes a calendar to each work centre:
| W/C | Calendar
| 1 | Calendar 1
| 2 | Calendar 2
|  |  | Start of first job: |  |  | 2000-03-14 08:30
W/C | Seq | Calendar | Jobs | Hours | Days | Start | Calc1 | Calc2 | Calc3 | Stop
1 | 1 | Calendar 1 | job A | 7 | 0.29167 | 2000-03-14 08:30 | #REF! | #REF! | #REF! | #REF!
1 | 2 | Calendar 1 | job C | 4 | 0.16667 | #REF! | #REF! | #REF! | #REF! | #REF!
1 | 3 | Calendar 1 | job D | 5 | 0.20833 | #REF! | #REF! | #REF! | #REF! | #REF!
2 | 1 | Calendar 2 | job E | 8 | 0.33333 | 2000-03-14 08:30 | #REF! | #REF! | #REF! | #REF!
2 | 2 | Calendar 2 | job B | 12 | 0.5 | #REF! | #REF! | #REF! | #REF! | #REF!
2 | 3 | Calendar 2 | job F | 6 | 0.25 | #REF! | #REF! | #REF! | #REF! | #REF!
| =VLOOKUP(A12,A$6:B$7,2) |  |  | look up the work centre in the table above, and return the contents of the 2nd column
| =MATCH(I12+F12,INDIRECT("'"&C12&"'!E5:E40"))+1 | [5 empty] | an example of indirect reference to the calendars
Formulas:
Start = IF([W/C]=[W/C, row above],[Stop, row above],G9)

## Calendar 1
Calendar with an Evening Shift
Hours | Day | Begin | End | Cum Days
2 | Mon | 2000-03-13 08:00 | 2000-03-13 10:00 | 0.083333
2.75 | Mon | 2000-03-13 10:15 | 2000-03-13 13:00 | 0.19792
2 | Mon | 2000-03-13 13:30 | 2000-03-13 15:30 | 0.28125
2.25 | Mon | 2000-03-13 15:45 | 2000-03-13 18:00 | 0.375
3 | Mon | 2000-03-13 19:00 | 2000-03-13 22:00 | 0.5
2 | Tue | 2000-03-14 08:00 | 2000-03-14 10:00 | 0.58333
2.75 | Tue | 2000-03-14 10:15 | 2000-03-14 13:00 | 0.69792
2 | Tue | 2000-03-14 13:30 | 2000-03-14 15:30 | 0.78125
2.25 | Tue | 2000-03-14 15:45 | 2000-03-14 18:00 | 0.875
3 | Tue | 2000-03-14 19:00 | 2000-03-14 22:00 | 1
2 | Wed | 2000-03-15 08:00 | 2000-03-15 10:00 | 1.0833
2.75 | Wed | 2000-03-15 10:15 | 2000-03-15 13:00 | 1.1979
2 | Wed | 2000-03-15 13:30 | 2000-03-15 15:30 | 1.2812
2.25 | Wed | 2000-03-15 15:45 | 2000-03-15 18:00 | 1.375
3 | Wed | 2000-03-15 19:00 | 2000-03-15 22:00 | 1.5
2 | Thu | 2000-03-16 08:00 | 2000-03-16 10:00 | 1.5833
2.75 | Thu | 2000-03-16 10:15 | 2000-03-16 13:00 | 1.6979
2 | Thu | 2000-03-16 13:30 | 2000-03-16 15:30 | 1.7812
2.25 | Thu | 2000-03-16 15:45 | 2000-03-16 18:00 | 1.875
3 | Thu | 2000-03-16 19:00 | 2000-03-16 22:00 | 2
2 | Fri | 2000-03-17 08:00 | 2000-03-17 10:00 | 2.0833
2.75 | Fri | 2000-03-17 10:15 | 2000-03-17 13:00 | 2.1979
2 | Fri | 2000-03-17 13:30 | 2000-03-17 15:30 | 2.2812
2.25 | Fri | 2000-03-17 15:45 | 2000-03-17 18:00 | 2.375
2 | Mon | 2000-03-20 08:00 | 2000-03-20 10:00 | 2.4583
2.75 | Mon | 2000-03-20 10:15 | 2000-03-20 13:00 | 2.5729
2 | Mon | 2000-03-20 13:30 | 2000-03-20 15:30 | 2.6562
2.25 | Mon | 2000-03-20 15:45 | 2000-03-20 18:00 | 2.75
3 | Mon | 2000-03-20 19:00 | 2000-03-20 22:00 | 2.875
2 | Tue | 2000-03-21 08:00 | 2000-03-21 10:00 | 2.9583
2.75 | Tue | 2000-03-21 10:15 | 2000-03-21 13:00 | 3.0729
2 | Tue | 2000-03-21 13:30 | 2000-03-21 15:30 | 3.1562
2.25 | Tue | 2000-03-21 15:45 | 2000-03-21 18:00 | 3.25
3 | Tue | 2000-03-21 19:00 | 2000-03-21 22:00 | 3.375
2 | Wed | 2000-03-22 08:00 | 2000-03-22 10:00 | 3.4583
2.75 | Wed | 2000-03-22 10:15 | 2000-03-22 13:00 | 3.5729
2 | Wed | 2000-03-22 13:30 | 2000-03-22 15:30 | 3.6562
2.25 | Wed | 2000-03-22 15:45 | 2000-03-22 18:00 | 3.75
3 | Wed | 2000-03-22 19:00 | 2000-03-22 22:00 | 3.875
2 | Thu | 2000-03-23 08:00 | 2000-03-23 10:00 | 3.9583
2.75 | Thu | 2000-03-23 10:15 | 2000-03-23 13:00 | 4.0729
2 | Thu | 2000-03-23 13:30 | 2000-03-23 15:30 | 4.1562
2.25 | Thu | 2000-03-23 15:45 | 2000-03-23 18:00 | 4.25
3 | Thu | 2000-03-23 19:00 | 2000-03-23 22:00 | 4.375
2 | Fri | 2000-03-24 08:00 | 2000-03-24 10:00 | 4.4583
2.75 | Fri | 2000-03-24 10:15 | 2000-03-24 13:00 | 4.5729
2 | Fri | 2000-03-24 13:30 | 2000-03-24 15:30 | 4.6562
2.25 | Fri | 2000-03-24 15:45 | 2000-03-24 18:00 | 4.75
2 | Mon | 2000-03-27 08:00 | 2000-03-27 10:00 | 4.8333
2.75 | Mon | 2000-03-27 10:15 | 2000-03-27 13:00 | 4.9479
2 | Mon | 2000-03-27 13:30 | 2000-03-27 15:30 | 5.0312
2.25 | Mon | 2000-03-27 15:45 | 2000-03-27 18:00 | 5.125
3 | Mon | 2000-03-27 19:00 | 2000-03-27 22:00 | 5.25
2 | Tue | 2000-03-28 08:00 | 2000-03-28 10:00 | 5.3333
2.75 | Tue | 2000-03-28 10:15 | 2000-03-28 13:00 | 5.4479
2 | Tue | 2000-03-28 13:30 | 2000-03-28 15:30 | 5.5312
2.25 | Tue | 2000-03-28 15:45 | 2000-03-28 18:00 | 5.625
3 | Tue | 2000-03-28 19:00 | 2000-03-28 22:00 | 5.75
2 | Wed | 2000-03-29 08:00 | 2000-03-29 10:00 | 5.8333
2.75 | Wed | 2000-03-29 10:15 | 2000-03-29 13:00 | 5.9479
2 | Wed | 2000-03-29 13:30 | 2000-03-29 15:30 | 6.0312
2.25 | Wed | 2000-03-29 15:45 | 2000-03-29 18:00 | 6.125
3 | Wed | 2000-03-29 19:00 | 2000-03-29 22:00 | 6.25
2 | Thu | 2000-03-30 08:00 | 2000-03-30 10:00 | 6.3333
2.75 | Thu | 2000-03-30 10:15 | 2000-03-30 13:00 | 6.4479
2 | Thu | 2000-03-30 13:30 | 2000-03-30 15:30 | 6.5312
2.25 | Thu | 2000-03-30 15:45 | 2000-03-30 18:00 | 6.625
3 | Thu | 2000-03-30 19:00 | 2000-03-30 22:00 | 6.75
2 | Fri | 2000-03-31 08:00 | 2000-03-31 10:00 | 6.8333
2.75 | Fri | 2000-03-31 10:15 | 2000-03-31 13:00 | 6.9479
2 | Fri | 2000-03-31 13:30 | 2000-03-31 15:30 | 7.0312
2.25 | Fri | 2000-03-31 15:45 | 2000-03-31 18:00 | 7.125
2 | Mon | 2000-04-03 08:00 | 2000-04-03 10:00 | 7.2083
2.75 | Mon | 2000-04-03 10:15 | 2000-04-03 13:00 | 7.3229
2 | Mon | 2000-04-03 13:30 | 2000-04-03 15:30 | 7.4062
2.25 | Mon | 2000-04-03 15:45 | 2000-04-03 18:00 | 7.5
3 | Mon | 2000-04-03 19:00 | 2000-04-03 22:00 | 7.625
2 | Tue | 2000-04-04 08:00 | 2000-04-04 10:00 | 7.7083
2.75 | Tue | 2000-04-04 10:15 | 2000-04-04 13:00 | 7.8229
2 | Tue | 2000-04-04 13:30 | 2000-04-04 15:30 | 7.9062
2.25 | Tue | 2000-04-04 15:45 | 2000-04-04 18:00 | 8
3 | Tue | 2000-04-04 19:00 | 2000-04-04 22:00 | 8.125
2 | Wed | 2000-04-05 08:00 | 2000-04-05 10:00 | 8.2083
2.75 | Wed | 2000-04-05 10:15 | 2000-04-05 13:00 | 8.3229
2 | Wed | 2000-04-05 13:30 | 2000-04-05 15:30 | 8.4062
2.25 | Wed | 2000-04-05 15:45 | 2000-04-05 18:00 | 8.5
3 | Wed | 2000-04-05 19:00 | 2000-04-05 22:00 | 8.625
2 | Thu | 2000-04-06 08:00 | 2000-04-06 10:00 | 8.7083
2.75 | Thu | 2000-04-06 10:15 | 2000-04-06 13:00 | 8.8229
2 | Thu | 2000-04-06 13:30 | 2000-04-06 15:30 | 8.9062
2.25 | Thu | 2000-04-06 15:45 | 2000-04-06 18:00 | 9
3 | Thu | 2000-04-06 19:00 | 2000-04-06 22:00 | 9.125
2 | Fri | 2000-04-07 08:00 | 2000-04-07 10:00 | 9.2083
2.75 | Fri | 2000-04-07 10:15 | 2000-04-07 13:00 | 9.3229
2 | Fri | 2000-04-07 13:30 | 2000-04-07 15:30 | 9.4062

## Calendar 2
Calendar Without an Evening Shift and Early End on a Friday
Hours | Day | Begin | End | Cum Days
2 | Mon | 2000-03-13 08:00 | 2000-03-13 10:00 | 0.083333
2.75 | Mon | 2000-03-13 10:15 | 2000-03-13 13:00 | 0.19792
2 | Mon | 2000-03-13 13:30 | 2000-03-13 15:30 | 0.28125
2.25 | Mon | 2000-03-13 15:45 | 2000-03-13 18:00 | 0.375
2 | Tue | 2000-03-14 08:00 | 2000-03-14 10:00 | 0.45833
2.75 | Tue | 2000-03-14 10:15 | 2000-03-14 13:00 | 0.57292
2 | Tue | 2000-03-14 13:30 | 2000-03-14 15:30 | 0.65625
2.25 | Tue | 2000-03-14 15:45 | 2000-03-14 18:00 | 0.75
2 | Wed | 2000-03-15 08:00 | 2000-03-15 10:00 | 0.83333
2.75 | Wed | 2000-03-15 10:15 | 2000-03-15 13:00 | 0.94792
2 | Wed | 2000-03-15 13:30 | 2000-03-15 15:30 | 1.0312
2.25 | Wed | 2000-03-15 15:45 | 2000-03-15 18:00 | 1.125
2 | Thu | 2000-03-16 08:00 | 2000-03-16 10:00 | 1.2083
2.75 | Thu | 2000-03-16 10:15 | 2000-03-16 13:00 | 1.3229
2 | Thu | 2000-03-16 13:30 | 2000-03-16 15:30 | 1.4062
2.25 | Thu | 2000-03-16 15:45 | 2000-03-16 18:00 | 1.5
2 | Fri | 2000-03-17 08:00 | 2000-03-17 10:00 | 1.5833
2.75 | Fri | 2000-03-17 10:15 | 2000-03-17 13:00 | 1.6979
2 | Fri | 2000-03-17 13:30 | 2000-03-17 15:30 | 1.7812
1.25 | Fri | 2000-03-17 15:45 | 2000-03-17 17:00 | 1.8333
2 | Mon | 2000-03-20 08:00 | 2000-03-20 10:00 | 1.9167
2.75 | Mon | 2000-03-20 10:15 | 2000-03-20 13:00 | 2.0312
2 | Mon | 2000-03-20 13:30 | 2000-03-20 15:30 | 2.1146
2.25 | Mon | 2000-03-20 15:45 | 2000-03-20 18:00 | 2.2083
2 | Tue | 2000-03-21 08:00 | 2000-03-21 10:00 | 2.2917
2.75 | Tue | 2000-03-21 10:15 | 2000-03-21 13:00 | 2.4062
2 | Tue | 2000-03-21 13:30 | 2000-03-21 15:30 | 2.4896
2.25 | Tue | 2000-03-21 15:45 | 2000-03-21 18:00 | 2.5833
2 | Wed | 2000-03-22 08:00 | 2000-03-22 10:00 | 2.6667
2.75 | Wed | 2000-03-22 10:15 | 2000-03-22 13:00 | 2.7812
2 | Wed | 2000-03-22 13:30 | 2000-03-22 15:30 | 2.8646
2.25 | Wed | 2000-03-22 15:45 | 2000-03-22 18:00 | 2.9583
2 | Thu | 2000-03-23 08:00 | 2000-03-23 10:00 | 3.0417
2.75 | Thu | 2000-03-23 10:15 | 2000-03-23 13:00 | 3.1562
2 | Thu | 2000-03-23 13:30 | 2000-03-23 15:30 | 3.2396
2.25 | Thu | 2000-03-23 15:45 | 2000-03-23 18:00 | 3.3333
2 | Fri | 2000-03-24 08:00 | 2000-03-24 10:00 | 3.4167
2.75 | Fri | 2000-03-24 10:15 | 2000-03-24 13:00 | 3.5312
2 | Fri | 2000-03-24 13:30 | 2000-03-24 15:30 | 3.6146
1.25 | Fri | 2000-03-24 15:45 | 2000-03-24 17:00 | 3.6667
2 | Mon | 2000-03-27 08:00 | 2000-03-27 10:00 | 3.75
2.75 | Mon | 2000-03-27 10:15 | 2000-03-27 13:00 | 3.8646
2 | Mon | 2000-03-27 13:30 | 2000-03-27 15:30 | 3.9479
2.25 | Mon | 2000-03-27 15:45 | 2000-03-27 18:00 | 4.0417
2 | Tue | 2000-03-28 08:00 | 2000-03-28 10:00 | 4.125
2.75 | Tue | 2000-03-28 10:15 | 2000-03-28 13:00 | 4.2396
2 | Tue | 2000-03-28 13:30 | 2000-03-28 15:30 | 4.3229
2.25 | Tue | 2000-03-28 15:45 | 2000-03-28 18:00 | 4.4167
2 | Wed | 2000-03-29 08:00 | 2000-03-29 10:00 | 4.5
2.75 | Wed | 2000-03-29 10:15 | 2000-03-29 13:00 | 4.6146
2 | Wed | 2000-03-29 13:30 | 2000-03-29 15:30 | 4.6979
2.25 | Wed | 2000-03-29 15:45 | 2000-03-29 18:00 | 4.7917
2 | Thu | 2000-03-30 08:00 | 2000-03-30 10:00 | 4.875
2.75 | Thu | 2000-03-30 10:15 | 2000-03-30 13:00 | 4.9896
2 | Thu | 2000-03-30 13:30 | 2000-03-30 15:30 | 5.0729
2.25 | Thu | 2000-03-30 15:45 | 2000-03-30 18:00 | 5.1667
2 | Fri | 2000-03-31 08:00 | 2000-03-31 10:00 | 5.25
2.75 | Fri | 2000-03-31 10:15 | 2000-03-31 13:00 | 5.3646
2 | Fri | 2000-03-31 13:30 | 2000-03-31 15:30 | 5.4479
1.25 | Fri | 2000-03-31 15:45 | 2000-03-31 17:00 | 5.5
2 | Mon | 2000-04-03 08:00 | 2000-04-03 10:00 | 5.5833
2.75 | Mon | 2000-04-03 10:15 | 2000-04-03 13:00 | 5.6979
2 | Mon | 2000-04-03 13:30 | 2000-04-03 15:30 | 5.7812
2.25 | Mon | 2000-04-03 15:45 | 2000-04-03 18:00 | 5.875
2 | Tue | 2000-04-04 08:00 | 2000-04-04 10:00 | 5.9583
2.75 | Tue | 2000-04-04 10:15 | 2000-04-04 13:00 | 6.0729
2 | Tue | 2000-04-04 13:30 | 2000-04-04 15:30 | 6.1562
2.25 | Tue | 2000-04-04 15:45 | 2000-04-04 18:00 | 6.25
2 | Wed | 2000-04-05 08:00 | 2000-04-05 10:00 | 6.3333
2.75 | Wed | 2000-04-05 10:15 | 2000-04-05 13:00 | 6.4479
2 | Wed | 2000-04-05 13:30 | 2000-04-05 15:30 | 6.5312
2.25 | Wed | 2000-04-05 15:45 | 2000-04-05 18:00 | 6.625
2 | Thu | 2000-04-06 08:00 | 2000-04-06 10:00 | 6.7083
2.75 | Thu | 2000-04-06 10:15 | 2000-04-06 13:00 | 6.8229
2 | Thu | 2000-04-06 13:30 | 2000-04-06 15:30 | 6.9062
2.25 | Thu | 2000-04-06 15:45 | 2000-04-06 18:00 | 7
2 | Fri | 2000-04-07 08:00 | 2000-04-07 10:00 | 7.0833
2.75 | Fri | 2000-04-07 10:15 | 2000-04-07 13:00 | 7.1979
2 | Fri | 2000-04-07 13:30 | 2000-04-07 15:30 | 7.2812
1.25 | Fri | 2000-04-07 15:45 | 2000-04-07 17:00 | 7.3333
2 | Mon | 2000-04-10 08:00 | 2000-04-10 10:00 | 7.4167
2.75 | Mon | 2000-04-10 10:15 | 2000-04-10 13:00 | 7.5312
2 | Mon | 2000-04-10 13:30 | 2000-04-10 15:30 | 7.6146
2.25 | Mon | 2000-04-10 15:45 | 2000-04-10 18:00 | 7.7083
2 | Tue | 2000-04-11 08:00 | 2000-04-11 10:00 | 7.7917
2.75 | Tue | 2000-04-11 10:15 | 2000-04-11 13:00 | 7.9062
2 | Tue | 2000-04-11 13:30 | 2000-04-11 15:30 | 7.9896
2.25 | Tue | 2000-04-11 15:45 | 2000-04-11 18:00 | 8.0833
2 | Wed | 2000-04-12 08:00 | 2000-04-12 10:00 | 8.1667
2.75 | Wed | 2000-04-12 10:15 | 2000-04-12 13:00 | 8.2812
2 | Wed | 2000-04-12 13:30 | 2000-04-12 15:30 | 8.3646
2.25 | Wed | 2000-04-12 15:45 | 2000-04-12 18:00 | 8.4583
2 | Thu | 2000-04-13 08:00 | 2000-04-13 10:00 | 8.5417
2.75 | Thu | 2000-04-13 10:15 | 2000-04-13 13:00 | 8.6562
2 | Thu | 2000-04-13 13:30 | 2000-04-13 15:30 | 8.7396
2.25 | Thu | 2000-04-13 15:45 | 2000-04-13 18:00 | 8.8333
2 | Fri | 2000-04-14 08:00 | 2000-04-14 10:00 | 8.9167
2.75 | Fri | 2000-04-14 10:15 | 2000-04-14 13:00 | 9.0312
2 | Fri | 2000-04-14 13:30 | 2000-04-14 15:30 | 9.1146
1.25 | Fri | 2000-04-14 15:45 | 2000-04-14 17:00 | 9.1667

## Section 13
Repetitive Production and Setups
So far we have accepted that a job has a duration of say, 7 hours, and we haven't worried about how the 7 hours has been estimated. Let's say the first job is to set up a work centre and then produce 500 of Product A. Work Centre 1 is an old machine which runs slowly, but is quick to set up, and Work Centre 2 is a new high speed machine, but the set ups take a long time. We would describe this in tables like this:
Units per hour
| W/C | Set up hours |  | Product | W/C 1 | W/C 2
| 1 | 1.25 |  | Prod A | 80 | 140
| 2 | 3 |  | Prod B | 55 | 105
|  |  |  | Prod C | 72 | 135
|  |  |  | Prod D | 65 | 110
The left hand side of the schedule would look like this
W/C | Seq | Product | Qty | Set up hours | Units per hour | Run hours | Total Hours | Days
1 | 1 | Prod D | 200 | 1.25 | 65 | 3.0769 | 4.3269 | 0.18029
1 | 2 | Prod B | 350 | 1.25 | 55 | 6.3636 | 7.6136 | 0.31723
1 | 3 | Prod A | 450 | 1.25 | 80 | 5.625 | 6.875 | 0.28646
1 | 4 | Prod B | 300 | 1.25 | 55 | 5.4545 | 6.7045 | 0.27936
2 | 1 | Prod C | 1500 | 3 | 135 | 11.1111 | 14.1111 | 0.58796
2 | 2 | Prod D | 1100 | 3 | 110 | 10 | 13 | 0.54167
=VLOOKUP(A18,B$8:C$9,2) |  |  |  |  | - look up the work centre, 2nd column
=VLOOKUP(C18,E$8:G$11,A18+1) |  |  |  |  | - look up the product, 2nd column for W/C 1, and
3rd column for W/C 2
=D18/F18 |  |  |  |  | - run hours is quantity divided by units per hour
=E18+G18 |  |  |  |  | - total hour is set up plus run

## Section 14
A Set-up Matrix
Often the time it takes to set up a work centre is dependant on the previous job. For example to clean out a mixer to make white paint, after it has been used to make black paint, will take a long time, but to change to grey paint after making white won't take as long. Similar examples exist in printing and food processing and with the shut height of presses. In these industries the sequence of the jobs will effect the amount of time the work centres are being set up, and therefore the productivity of the work centres.
The set-up times between products, or product groups is expressed in a matrix as follows:
| Work Centre 1 - minutes |  |  |  |  | Work Centre 2 - minutes
|  | Prod A | Prod B | Prod C | Prod D |  | Prod A | Prod B | Prod C | Prod D
| Prod A | 0 | 0.5 | 0.5 | 1.25 | Prod A | 0 | 1.25 | 1.25 | 2.75
| Prod B | 2 | 0 | 0.75 | 1 | Prod B | 4.25 | 0 | 1.75 | 2.5
| Prod C | 2 | 2 | 0 | 0.75 | Prod C | 4.25 | 4.25 | 0 | 1.75
| Prod D | 2.1 | 1.75 | 1.5 | 0 | Prod D | 5 | 4.5 | 3.5 | 0
In Lotus 123 there is a handy function, XINDEX for referencing a value in a matrix, but in Excel we will do it with a combination of =MATCH and =VLOOKUP. First we need to name 4 ranges with Insert¦Name¦Define:
| Top_row_1 |  |  | Top_row_2
| Matrix_1 |  |  | Matrix_2
Use the name box to the left of the formula bar to see where the named ranges are.
The problem is to retrieve a set-up time given the following values
Work Centre |  |  | 1
Previous product |  |  | Prod D
This Product |  |  | Prod B
name of top row |  |  |  |  | Top_row_1 | ="Top_row_"&D23
name of matrix |  |  |  |  | Matrix_1 | ="Matrix_"&D23
position of this product in top row |  |  |  |  | 3 | =MATCH(D25,INDIRECT(F27))
look up previous product in matrix |  |  |  |  | 1.75 | =VLOOKUP(D24,INDIRECT(F28),F29)
Put it all together and we get:
=VLOOKUP(D24,INDIRECT("Matrix_"&D23),MATCH(D25,INDIRECT("Top_row_"&D23)))
If we apply this formula to the first product scheduled on the work centre, then it won't work because there isn't a previous product. We will assume that the first product scheduled on the work centre is already running, so the set-up time is zero. We will test if it is the first product using the =IF function.
from
to
from
to

## Section 15
Applying the Set-up Matrix Formula
Here is the schedule from Section 13 again, but this time the set-up times are derived from the
matrixes:
W/C | Seq | Product | Qty | Set-up hours | Units per hour | Run hours | Total Hours | Days
1 | 1 | Prod D | 200 | 0 | 65 | 3.0769 | 3.0769 | 0.12821
1 | 2 | Prod B | 350 | 1.75 | 55 | 6.3636 | 8.1136 | 0.33807
1 | 3 | Prod A | 450 | 2 | 80 | 5.625 | 7.625 | 0.31771
1 | 4 | Prod B | 300 | 0.5 | 55 | 5.4545 | 5.9545 | 0.24811
2 | 1 | Prod C | 1500 | 0 | 135 | 11.1111 | 11.1111 | 0.46296
2 | 2 | Prod D | 1100 | 1.75 | 110 | 10 | 11.75 | 0.48958
|  | Totals: |  | 6 |  | 41.6312
=IF(A7=A6,VLOOKUP(C6,INDIRECT("Matrix_"&A7),MATCH(C7,INDIRECT("Top_row_"&A7))),0)
Try changing the sequence numbers and sorting to see if you can reduce the total set-up hours

## Section 16
Gantt Chart 2 - Hours per Day
In the simple Gantt chart in Section 4 each time bucket is one hour long, and the jobs fall conveniently in or out of a bucket
This Gantt chart shows daily buckets, and the number of hours in a day is determined by the calendar. The start and stop of each
job is compared with the beginning and end of each day, to determine what portion of the job falls within the day, as follows:
9 |  |  |  | =IF(AND($K36>L$30,$K36<M$30),$K36-L$30,L$34)
if the job stops during the day, job stop minus day begin, else hours in the day
9 |  |  |  | =IF(AND($J36>=L$30,$J36<M$30),M$30-$J36,A8)
if the job starts during the day, day end minus job start, else above
9 |  |  |  | =IF(AND($J36>=L$30,$K36<M$30),$C36,A12)
if the job starts and stops within the day, the job hours, else above
9 |  |  |  | =IF(OR($K36<=L$30,$J36>=M$30),"",A15)
if the job stops before the day begins, or starts after the day ends, blank, else above
The 4 IF statements above have been "nested" into one
=(VLOOKUP(M32,'Calendar 2'!$C$5:$E$110,3)-$J32)*24
hours into the schedule - cumulative day less 1st cumulative day, converted to hours
=INT(E32) |  |  |  | the midnight before the start of the first job
| =VLOOKUP(I32,'Calendar 2'!C6:E110,3) | [7 empty] | look up the cumulative days in the calendar | [7 empty] | =M30-L30
[9 empty] | =L32+1 | previous day plus 1 | [6 empty] | hours in the day
[11 empty] | 0 | 9 | 18 | 27 | 35 | 35 | 35 | 44 | 53 | 62 | 71 | 79 | 79 | 79 | 88 | 97 | 106
Start of first job: |  |  |  | 2000-03-14 08:00 |  |  |  | 2000-03-14 | 0.375 |  | 2000-03-14 | 2000-03-15 | 2000-03-16 | 2000-03-17 | 2000-03-18 | 2000-03-19 | 2000-03-20 | 2000-03-21 | 2000-03-22 | 2000-03-23 | 2000-03-24 | 2000-03-25 | 2000-03-26 | 2000-03-27 | 2000-03-28 | 2000-03-29 | 2000-03-30
[11 empty] | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed
Seq | Jobs | Hrs | Days | Start | Calc1 | Calc2 | Calc3 | Stop | Start hr | Stop hr | 9 | 9 | 9 | 8 | 0 | 0 | 9 | 9 | 9 | 9 | 8 | 0 | 0 | 9 | 9 | 9
1 | job A | 10.5 | 0.4375 | 2000-03-14 08:00 | 1900-01-05 | 0.8125 | 1900-01-09 | 2000-03-15 09:30 | 0 | 10.5 | 2000-03-14: 9; 2000-03-15: 1.5
2 | job B | 8 | 0.33333 | 2000-03-15 09:30 | 1900-01-09 | 1899-12-31 03:30 | 1900-01-13 | 2000-03-16 08:30 | 10.5 | 18.5 | 2000-03-15: 7.5; 2000-03-16: 0.5
3 | job C | 6.5 | 0.27083 | 2000-03-16 08:30 | 1900-01-13 | 1899-12-31 10:00 | 1900-01-16 | 2000-03-16 16:00 | 18.5 | 25 | 2000-03-16: 6.5
4 | job D | 16 | 0.66667 | 2000-03-16 16:00 | 1900-01-16 | 1900-01-01 02:00 | 1900-01-23 | 2000-03-20 14:45 | 25 | 41 | 2000-03-16: 2; 2000-03-17: 8; 2000-03-18: 0; 2000-03-19: 0; 2000-03-20: 6
5 | job E | 21.5 | 0.89583 | 2000-03-20 14:45 | 1900-01-23 | 1900-01-01 23:30 | 1900-02-02 | 2000-03-23 08:30 | 41 | 62.5 | 2000-03-20: 3; 2000-03-21: 9; 2000-03-22: 9; 2000-03-23: 0.5
6 | job F | 23 | 0.95833 | 2000-03-23 08:30 | 1900-02-02 | 1900-01-02 22:30 | 1900-02-12 | 2000-03-27 15:15 | 62.5 | 85.5 | 2000-03-23: 8.5; 2000-03-24: 8; 2000-03-25: 0; 2000-03-26: 0; 2000-03-27: 6.5
Hours into the schedule:
=K35 |  | start hour is the stop hour of the previous job
=J36+C36 |  | stop hour is start hour plus job hours
Note that columns F,G and H containing the calendar formulas, have been hidden
Look at Format¦Conditional Formatting to see how the shading is done
Change the hours or the sequence, then sort, to see how the Gantt chart responds
You can extend the Gantt chart by copying a column of formulas and pasting it to the right, and copying a row and pasting it downwards
Job
Job
Job
Job
Day
Job
Job
Day

## Section 17
Gantt Chart 3 - Units per Day
For repetitive production, you may wish to show the number of units that can be produced in a day, rather than the number
of hours of a job that falls into each day. The Gantt chart in Section 16 can be extended to do this, by multiplying the hours
by the units per hour. Lets take a repetitive production schedule, as in Section 15, but with one work centre:
[10 empty] | 0 | 9 | 18 | 27 | 35 | 35 | 35 | 44 | 53 | 62 | 71 | 79 | 79 | 79 | 88
Start of first job: |  |  | 2000-03-14 08:00 |  | 2000-03-14 |  |  | 0.375 |  | 2000-03-14 | 2000-03-15 | 2000-03-16 | 2000-03-17 | 2000-03-18 | 2000-03-19 | 2000-03-20 | 2000-03-21 | 2000-03-22 | 2000-03-23 | 2000-03-24 | 2000-03-25 | 2000-03-26 | 2000-03-27 | 2000-03-28
[10 empty] | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon
W/C | Seq | Product | Qty | Set-up hours | Units per hour | Run hours | Total Hours | Start hr | Stop hr | 9 | 9 | 9 | 8 | 0 | 0 | 9 | 9 | 9 | 9 | 8 | 0 | 0 | 9
2 | 1 | Prod D | 650 | 0 | 110 | 5.9091 | 5.9091 | 0 | 5.9091 | 2000-03-14: 650
2 | 2 | Prod B | 1200 | 4.5 | 105 | 11.4286 | 15.9286 | 10.4091 | 21.8377 | 2000-03-15: 797.0455; 2000-03-16: 402.9545
2 | 3 | Prod A | 2350 | 4.25 | 140 | 16.7857 | 21.0357 | 26.0877 | 42.8734 | 2000-03-16: 127.7273; 2000-03-17: 1120; 2000-03-18: 0; 2000-03-19: 0; 2000-03-20: 1102.2727
2 | 4 | Prod B | 300 | 1.25 | 105 | 2.8571 | 4.1071 | 44.1234 | 46.9805 | 2000-03-21: 300
2 | 5 | Prod C | 4500 | 1.75 | 135 | 33.3333 | 35.0833 | 48.7305 | 82.0639 | 2000-03-21: 576.3799; 2000-03-22: 1215; 2000-03-23: 1215; 2000-03-24: 1080; 2000-03-25: 0; 2000-03-26: 0; 2000-03-27: 413.6201
The stop and start hours for each job are the hours into the schedule during which items will actually be produced, and exclude
the set-up hours.
=J13+E14 |  |  | start hour is the stop hour of the previous job plus the set-up hours
=I14+G14 |  |  | stop hour is start hour plus run hours
=IF(OR($J14<=K$8,$I14>=L$8),"",IF(AND($I14>=K$8,$J14<L$8),$G14,IF(AND($I14>=K$8,$I14<L$8),L$8-$I14,IF(AND($J14>K$8,$J14<L$8),$J14-K$8,K$12)))*$F14)
Same nested IF formula as in Section 16, but multiplied by Units per Hour
This report is useful as a production target to be issued at the beginning of a week, as it is easy to compare actual performance
against it. In setting a production target for a day, it takes into account:
- calendar hours each day (production is lower on a Friday)
- each product runs at a different speed
- the set-up time depends on the previous product

## Section 18
Working Hours Between Two Dates (Calendar Formula 2)
The more observant of you may have noticed a problem with the last two Gantt charts. They are fine as long as the start of the first job coincides with beginning of the day, but if you go to Section 16 and change the start time to, say 10:00 AM, then there are still 9 hours used on the first day, that can't be right. If the first job starts at 10:00 AM, then the Start Hr of job A should be 2, the 2nd hour of the schedule. However, if the first job starts at 2:00 PM, then that is 5.25 hours into the schedule because according to Calendar 2 there is a 15 minute morning break and a 30 min lunch break in between.
What we need is a formula that takes two points in time and calculates how many working hours (days x 24) there are between the two points. The calculation is very similar to that in Section 6:
Period Number | Begin | End | Working Hours | Working Hours so far (Cum)
1 | 0 | 0 | 0 | 0
2 | 8 | 10 | 2 | 2
3 | 10.25 | 13 | 2.75 | 4.75
4 | 13.5 | 15.5 | 2 | 6.75
5 | 15.75 | 18 | 2.25 | 9
6 | 19 | 22 | 3 | 12
The first 9 stages of the calculation locate the start on the calendar, and they are repeated for the stop:
[5 empty] | Start | Stop
[5 empty] | 8.5 | 18.5
Stages of the calculation: |  |  |  |  | (8:30 AM) | (6:30 PM)
8:30 AM is after period 2 begins, (6:30 PM is after period 5 begins) |  |  |  |  | 2 | 5 | =MATCH(H20,B10:B15)
8:30 AM is after period 1 ends, (6:30 PM is after period 5 ends) |  |  |  |  | 1 | 5 | =MATCH(H20,C10:C15)
8:30 AM (6:30 PM) lies between the beginning and end of period 2, (6) |  |  |  |  | 2 | 6 | =H23+(H23=H24)
period 2 begins at 8:00 AM, (period 6 begins at 7:00 PM) |  |  |  |  | 8 | 19 | =INDEX(B10:B15,H25,1)
period 2 ends at 10:00 AM, (period 6 ends at 10:00 PM) |  |  |  |  | 10 | 22 | =INDEX(C10:C15,H25,1)
you can start at 8:30 AM, (stop at 7:00 PM) because it's within a working period |  |  |  |  | 8.5 | 19 | =MAX(H26,H20)
the number of hours from the start to the next break |  |  |  |  | 1.5 | 3 | =H27-H28
cum hours at end of period 2, (12) |  |  |  |  | 2 | 12 | =INDEX(E10:E15,H25,1)
the start is at cum hour 0.5 of the calendar, (the stop is at cum hour 9) |  |  |  |  | 0.5 | 9 | =H30-H29
working hours between the Start and Stop, (9 - 0.5) | [5 empty] | 8.5 | =H31-G31
With a series of substitutions, the 19 formulas can be condensed into 4 as follows:
Calc 4 | 2 | =MATCH(G20,B10:B15)+(MATCH(G20,B10:B15)=MATCH(G20,C10:C15))
Calc 5 | 0.5 | =INDEX(E10:E15,B37,1)-INDEX(C10:C15,B37,1)+MAX(INDEX(B10:B15,B37,1),G20)
Calc 6 | 6 | =MATCH(H20,B10:B15)+(MATCH(H20,B10:B15)=MATCH(H20,C10:C15))
Hours | 8.5 | =INDEX(E10:E15,B39,1)-INDEX(C10:C15,B39,1)+MAX(INDEX(B10:B15,B39,1),H20)-B38

## Section 19
Applying Calendar Formula 2
Here is the Gantt Chart from Section 17 again, but this time it recognises that the first job may not start at the beginning of the first day.
Start of first job: |  |  | 2000-03-14 10:00 |  | 2000-03-14 |  |  | 0.375
[10 empty] | 0 | 9 | 18 | 27 | 35 | 35 | 35 | 44 | 53 | 62 | 71 | 79 | 79 | 79 | 88
|  |  | Calc 4 | Calc 5 | Calc 6
|  |  | 6 | 0.375 | 7 |  |  |  |  | 2000-03-14 | 2000-03-15 | 2000-03-16 | 2000-03-17 | 2000-03-18 | 2000-03-19 | 2000-03-20 | 2000-03-21 | 2000-03-22 | 2000-03-23 | 2000-03-24 | 2000-03-25 | 2000-03-26 | 2000-03-27 | 2000-03-28
[10 empty] | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon
W/C | Seq | Product | Qty | Set-up hours | Units per hour | Run hours | Total Hours | Start hr | Stop hr | 9 | 9 | 9 | 8 | 0 | 0 | 9 | 9 | 9 | 9 | 8 | 0 | 0 | 9
2
2 | 1 | Prod D | 650 | 0 | 110 | 5.9091 | 5.9091 | 2 | 7.9091 | 2000-03-14: 650
2 | 2 | Prod B | 1200 | 4.5 | 105 | 11.4286 | 15.9286 | 12.4091 | 23.8377 | 2000-03-15: 587.0455; 2000-03-16: 612.9545
2 | 3 | Prod A | 2350 | 4.25 | 140 | 16.7857 | 21.0357 | 28.0877 | 44.8734 | 2000-03-17: 967.7273; 2000-03-18: 0; 2000-03-19: 0; 2000-03-20: 1260; 2000-03-21: 122.2727
2 | 4 | Prod B | 300 | 1.25 | 105 | 2.8571 | 4.1071 | 46.1234 | 48.9805 | 2000-03-21: 300
2 | 5 | Prod C | 4500 | 1.75 | 135 | 33.3333 | 35.0833 | 50.7305 | 84.0639 | 2000-03-21: 306.3799; 2000-03-22: 1215; 2000-03-23: 1215; 2000-03-24: 1080; 2000-03-25: 0; 2000-03-26: 0; 2000-03-27: 683.6201
Working hours between 12:00 AM and 10:00 AM

## Section 20
Jobs That Pass Through Multiple Work Centres
So far we have considered jobs assigned to Work Centre 1 OR Work Centre 2, and now we shall look at jobs that pass through Work Centre 1 AND THEN Work Centre 2. To avoid
confusion lets have Work Centre 6 doing the 1st operation on the job, and Work Centre 7 the 2nd operation.
For the sake of simplicity our example will not refer to a calendar (the work centres operate 24 hours a day, 7 days a week) and we will not allow for set-up times.
Note the use of a 24 hour time format to fit into narrower columns.
size of time bucket in days (8 hours)
[11 empty] | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333
[7 empty] | Start of first job: |  | 2000-03-14 08:00
[11 empty] | 2000-03-14 |  |  | 2000-03-15 |  |  | 2000-03-16 |  |  | 2000-03-17
W/C | Jobs | Op | Job/Op | Dur-ation Hours | Previous Op | Previous Op Row | Stop of Previous Op | Wait hours | Start | Stop | 36599 | 36599.3333 | 36599.6667 | 36600 | 36600.3333 | 36600.6667 | 36601 | 36601.3333 | 36601.6667 | 36602 | 36602.3333 | 36602.6667 | 36603
6 | job A | 1 | A/1 | 19 | A/0 | #N/A | 1899-12-31 | 0 | 2000-03-14 08:00 | 2000-03-15 03:00 |  | 8 | 8 | 3
6 | job B | 1 | B/1 | 22 | B/0 | #N/A | 1899-12-31 | 0 | 2000-03-15 03:00 | 2000-03-16 01:00 |  |  |  | 5 | 8 | 8 | 1
6 | job C | 1 | C/1 | 17 | C/0 | #N/A | 1899-12-31 | 0 | 2000-03-16 01:00 | 2000-03-16 18:00 | [6 empty] | 7 | 8 | 2
7 | job A | 2 | A/2 | 8 | A/1 | 15 | 2000-03-15 03:00 | 19 | 2000-03-15 03:00 | 2000-03-15 11:00 |  |  |  | 5 | 3
7 | job B | 2 | B/2 | 14 | B/1 | 16 | 2000-03-16 01:00 | 14 | 2000-03-16 01:00 | 2000-03-16 15:00 | [6 empty] | 7 | 7
7 | job C | 2 | C/2 | 6 | C/1 | 17 | 2000-03-16 18:00 | 3 | 2000-03-16 18:00 | 2000-03-17 | [8 empty] | 6
8 | job A | 3 | A/3 | 13 | A/2 | 18 | 2000-03-15 11:00 | 27 | 2000-03-15 11:00 | 2000-03-16 |  |  |  |  | 5 | 8
8 | job B | 3 | B/3 | 11 | B/2 | 19 | 2000-03-16 15:00 | 15 | 2000-03-16 15:00 | 2000-03-17 02:00 | [7 empty] | 1 | 8 | 2
8 | job C | 3 | C/3 | 21 | C/2 | 20 | 2000-03-17 | 0 | 2000-03-17 02:00 | 2000-03-17 23:00 | [9 empty] | 6 | 8 | 7
=RIGHT(B15,1)&"/"&C15 | [5 empty] | - make a unique key to each row by taking the rightmost character of the job and concatenating it with the operation e.g. job A/operation 1
=RIGHT(B15,1)&"/"&(C15-1) | [5 empty] | - derive the previous operation by subtracting 1 from the operation number
=MATCH(F15,D$1:D$26,FALSE) | [5 empty] | - find the row number of the previous operation by looking down column D
=IF(ISERROR(G15),1,INDEX(K$1:K$26,G15,1)) | [5 empty] | - if ther is no previous op, then put day 1 (1 Jan 1900), else get the stop of the previous op from column K
=(J15-IF(A15=A14,K14,$J$12))*24 | [5 empty] | - the number of hours the wok centre has to wait for the previous operation to finish, before it can start
=MAX(IF(A15=A14,K14,$J$12),H15) | [5 empty] | - the start is later of: if it’s the same work centre, the stop of the previous job, else the start of the first job, and the stop of the previous operation
=J15+(E15/24) | [5 empty] | - the stop is the start plus hours converted to days
Note the gaps while the work centre waits for the prevoius operation to finish
This is a good point to talk about "The Theory of Constraints", and if you havn't yet read "The Goal" by Eli Goldratt, then you will find it a good introduction to the subject. Production managers who do not understand the theory of constraints, would become anxious when work centres 7 and 8 are not fully utilised. This kind of schedule will help them to understand that in order to get the work out of the door, they should only worry about the utilisation of a work centre while it is a constraint, and in this example, they should focus their attention on work centre 6 for the first two and a half days, and on work centre 8 for the last day and a half.

## Section 21
Repetitive Production that Passes Through Multiple Work Centres
In the example in Section 20, the 1st operation of a job had to be complete before the second operation could start. However if the job is to manufacture 5000 units, then often you don't have to wait for all of them to have gone through the 1st operation before you start the 2nd operation. When the first transfer batch (pallet load or bin full) of the product has come off the 1st work centre, it can be passed to the second work centre for the second operation to start while the product is still going through the 1st work centre.
A similar principle will apply at the end of the production run, when the last transfer batch (or part batch) of product comes off the first operation it will join a queue at the second operation. However if the second operation is faster (as in this example), then the first operation will stop, the transfer batch will be passed to the second operation, which will then stop after the transfer batch has been completed.
The rule that defines how long after the 1st operation the 2nd operation can start and stop, should be stated as the number of units in the transfer batch, but for the sake of simplicity, we will define it here as the time which the start and stop, of the next operation, lags behind the previous operation:
[15 empty] | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333
The next operation can start |  |  |  | 1 | hour after the start of the previous operation (Lag) |  |  |  |  | Start of first job: |  | 2000-03-14 04:00
[15 empty] | 2000-03-14 |  |  | 2000-03-15 |  |  | 2000-03-16 |  |  | 2000-03-17
W/C | Product | Op | Prod/Op | Qty | Units per Hour | Dur-ation Hours | Previous Op | Previous Op Row | Start of Previous Op | Stop of Previous Op | Wait hours | Start | Stop | Effective Units per Hour | 36599 | 36599.3333 | 36599.6667 | 36600 | 36600.3333 | 36600.6667 | 36601 | 36601.3333 | 36601.6667 | 36602 | 36602.3333 | 36602.6667 | 36603
6 | prod A | 1 | A/1 | 1500 | 65 | 23.0769 | A/0 | #N/A | 0 | 0 | 0 | 2000-03-14 04:00 | 2000-03-15 03:05 | 65 | 260 | 520 | 520 | 200
6 | prod B | 1 | B/1 | 2200 | 60 | 36.6667 | B/0 | #N/A | 0 | 0 | 0 | 2000-03-15 03:05 | 2000-03-16 15:45 | 60 |  |  |  | 295.3846 | 480 | 480 | 480 | 464.6154
6 | prod C | 1 | C/1 | 1900 | 75 | 25.3333 | C/0 | #N/A | 0 | 0 | 0 | 2000-03-16 15:45 | 2000-03-17 17:05 | 75 | [7 empty] | 19.2308 | 600 | 600 | 600 | 80.7692
7 | prod A | 2 | A/2 | 1500 | 105 | 14.2857 | A/1 | 14 | 2000-03-14 05:00 | 2000-03-15 04:05 | 1 | 2000-03-14 05:00 | 2000-03-15 04:05 | 65 | 195 | 520 | 520 | 265
7 | prod B | 2 | B/2 | 2200 | 95 | 23.1579 | B/1 | 15 | 2000-03-15 04:05 | 2000-03-16 16:45 | 0 | 2000-03-15 04:05 | 2000-03-16 16:45 | 60 |  |  |  | 235.3846 | 480 | 480 | 480 | 480 | 44.6154
7 | prod C | 2 | C/2 | 1900 | 110 | 17.2727 | C/1 | 16 | 2000-03-16 16:45 | 2000-03-17 18:05 | 0 | 2000-03-16 16:45 | 2000-03-17 18:05 | 75 | [8 empty] | 544.2308 | 600 | 600 | 155.7692
8 | prod A | 3 | A/3 | 1500 | 80 | 18.75 | A/2 | 17 | 2000-03-14 06:00 | 2000-03-15 05:05 | 2 | 2000-03-14 06:00 | 2000-03-15 05:05 | 65 | 130 | 520 | 520 | 330
8 | prod B | 3 | B/3 | 2200 | 85 | 25.8824 | B/2 | 18 | 2000-03-15 05:05 | 2000-03-16 17:45 | 0 | 2000-03-15 05:05 | 2000-03-16 17:45 | 60 |  |  |  | 175.3846 | 480 | 480 | 480 | 480 | 104.6154
8 | prod C | 3 | C/3 | 1900 | 95 | 20 | C/2 | 19 | 2000-03-16 17:45 | 2000-03-17 19:05 | 0 | 2000-03-16 17:45 | 2000-03-17 19:05 | 75 | [8 empty] | 469.2308 | 600 | 600 | 230.7692
=IF(ISERROR(I22),0,INDEX(M$1:M$25,I22,1)+(E$11/24)) | [6 empty] | - find the start of the previous operation in column M, and add 1 hour
=MAX(IF(A22=A21,N21,$M$11),J22) | [6 empty] | - the start is later of: if it’s the same work centre, the stop of the previous job, else the start of the first job, and the start of the previous operation
=MAX(M22+(G22/24),K22) | [6 empty] | - the stop is the later of: the start plus the hours, and the stop of the previous operation
=E22/(N22-M22)/24 | [6 empty] | - quantity divided by the stop minus the start
Although the second operation can start 1 hour after the first, it is faster and will quickly catch up. Work Centre 7 will then keep stopping to wait for products from the slower Work Centre 6,
and that is why the effective speed in units per hour is so much less than the rated speed. This is a typical "PUSH" schedule, but we discuss an alternative approach in later sections.

## Section 22
Transfer Batches
In Section 21 we assumed that the next operation starts and stops X hours after the previous operation starts and stops. In this example we use more sophisticated calculations. Each product has a different transfer batch size. The first transfer batch emerges from the previous operation after a time determined by the units per hour of the previous operation. It then takes X minutes to transfer the batch to the next work centre, so that the next operation can start. If the quantity to be produced is not a multiple of the transfer batch size, then the last batch will be smaller. The previous operation will stop, and the last batch will take X minutes to be transferred to the next work centre, where is will pass through the next operation after a time determined by the units per hour of the next operation.
|  |  | Batch size |  |  | Try changing the transfer batch sizes here and see what effect is has on the stop time of the last operation.
| prod A |  | 80
| prod B |  | 50
| prod C |  | 100
[19 empty] | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333
Time to transfer a batch between work centres: | [5 empty] | 5 | minutes | [6 empty] | Start of first job: |  | 2000-03-14 04:00
[19 empty] | 2000-03-14 |  |  | 2000-03-15 |  |  | 2000-03-16 |  |  | 2000-03-17
W/C | Product | Op | Prod/Op | Qty | Units per Hour | Dur-ation Hours | Previous Op | Previous Op Row | Batch size | 1 st Batch Lag | Last Batch Size | Last Batch Lag | Start of Previous Op | Stop of Previous Op | Wait hours | Start | Stop | Effective Units per Hour | 36599 | 36599.3333 | 36599.6667 | 36600 | 36600.3333 | 36600.6667 | 36601 | 36601.3333 | 36601.6667 | 36602 | 36602.3333 | 36602.6667 | 36603
6 | prod A | 1 | A/1 | 1500 | 65 | 23.0769 | A/0 | #N/A | 80 | 0 | 60 | 1.0064 | 0 | 0 | 0 | 2000-03-14 04:00 | 2000-03-15 03:05 | 65 | 260 | 520 | 520 | 200
6 | prod B | 1 | B/1 | 2200 | 60 | 36.6667 | B/0 | #N/A | 50 | 0 | 50 | 0.91667 | 0 | 0 | 0 | 2000-03-15 03:05 | 2000-03-16 15:45 | 60 |  |  |  | 295.3846 | 480 | 480 | 480 | 464.6154
6 | prod C | 1 | C/1 | 1900 | 75 | 25.3333 | C/0 | #N/A | 100 | 0 | 100 | 1.4167 | 0 | 0 | 0 | 2000-03-16 15:45 | 2000-03-17 17:05 | 75 | [7 empty] | 19.2308 | 600 | 600 | 600 | 80.7692
7 | prod A | 2 | A/2 | 1500 | 105 | 14.2857 | A/1 | 14 | 80 | 1.3141 | 60 | 0.65476 | 2000-03-14 05:19 | 2000-03-15 03:44 | 1.3141 | 2000-03-14 05:19 | 2000-03-15 03:44 | 66.9118 | 179.7181 | 535.2941 | 535.2941 | 249.6936
7 | prod B | 2 | B/2 | 2200 | 95 | 23.1579 | B/1 | 15 | 50 | 0.91667 | 50 | 0.60965 | 2000-03-15 04:00 | 2000-03-16 16:21 | 0.2619 | 2000-03-15 04:00 | 2000-03-16 16:21 | 60.5066 |  |  |  | 242.4144 | 484.0531 | 484.0531 | 484.0531 | 484.0531 | 21.3733
7 | prod C | 2 | C/2 | 1900 | 110 | 17.2727 | C/1 | 16 | 100 | 1.4167 | 100 | 0.99242 | 2000-03-16 17:10 | 2000-03-17 18:04 | 0.80702 | 2000-03-16 17:10 | 2000-03-17 18:04 | 76.2774 | [8 empty] | 521.7177 | 610.219 | 610.219 | 157.8444
8 | prod A | 3 | A/3 | 1500 | 80 | 18.75 | A/2 | 17 | 80 | 0.84524 | 60 | 0.83333 | 2000-03-14 06:10 | 2000-03-15 04:34 | 2.1593 | 2000-03-14 06:10 | 2000-03-15 04:34 | 66.9473 | 123.2272 | 535.5785 | 535.5785 | 305.6157
8 | prod B | 3 | B/3 | 2200 | 85 | 25.8824 | B/2 | 18 | 50 | 0.60965 | 50 | 0.67157 | 2000-03-15 04:36 | 2000-03-16 17:01 | 0.038221 | 2000-03-15 04:36 | 2000-03-16 17:01 | 60.4038 |  |  |  | 205.1772 | 483.2301 | 483.2301 | 483.2301 | 483.2301 | 61.9022
8 | prod C | 3 | C/3 | 1900 | 95 | 20 | C/2 | 19 | 100 | 0.99242 | 100 | 1.136 | 2000-03-16 18:09 | 2000-03-17 19:12 | 1.1279 | 2000-03-16 18:09 | 2000-03-17 19:12 | 75.8403 | [8 empty] | 443.4627 | 606.7227 | 606.7227 | 243.092
=VLOOKUP(B22,$B$7:$D$9,3) | [7 empty] | - look up the transfer batch size for the product from the table
=IF(ISERROR(I22),0,(J22/INDEX(F$1:F$25,I22,1))+(G$11/60)) | [7 empty] | - if there is a previous batch, find the speed in column F, and use it to calculate the time to produce the first batch, then add the transfer time, to get the Lag in hours
=IF(MOD(E22,J22),MOD(E22,J22),J22) | [7 empty] | - the last batch is the remainder after dividing the quantity by the batch size, if there is one, else return the batch size
=(G$11/60)+(L22/F22) | [7 empty] | - the transfer time plus the batch size divided by the units per hour, to get the Lag in hours
=IF(ISERROR(I22),0,INDEX(Q$1:Q$25,I22,1)+(K22/24)) | [7 empty] | - the start of the previous operation plus the time of the first batch
=IF(ISERROR(I22),0,INDEX(R$1:R$25,I22,1)+(M22/24)) | [7 empty] | - the stop of the previous operation, plus the time of the last batch

## Section 23
Re-Using Parts of the Calendar Formulas
In the next Section we will apply the calendar formulas to the schedule in Section 21, but before we do, lets look more closely at the formulas. You will notice that in Section 21 a duration is added to a start or stop, in three places:
- in column J, the lag duration is added to the start of the previous operation
- in column K, the lag duration is added to the stop of the previous operation
- in column N, the operation duration is added to the start
Here is an example of the calendar formulas applied to two durations from the same start:
Hours | Days | Start | Calc1 | Calc2 | Calc3 | Stop
7 | 0.29167 | 2000-03-15 09:30 | 9 | 0.8125 | 12 | 2000-03-15 17:30
1 | 0.041667 | 2000-03-15 09:30 | 9 | 0.8125 | 10 | 2000-03-15 10:45
Calc1 and Calc2 locate the start in the calendar and return the same values on each row, whereas Calc3 and Stop use the duration in days. So we could re-use Calc1 and Calc2 as follows:
Hours 1 | Days 1 | Start | Calc1 | Calc2 | Calc3 | Stop 1 | Hours 2 | Days 2 | Calc4 | Stop 2
7 | 0.29167 | 2000-03-15 09:30 | 9 | 0.8125 | 12 | 2000-03-15 17:30 | 1 | 0.041667 | 10 | 2000-03-15 10:45
Note how these formulas refer back to Calc2
=MATCH(E19+I19,'Calendar 2'!$E$6:$E$100)+1
=INDEX('Calendar 2'!$D$6:$D$100,J19,1)-INDEX('Calendar 2'!$E$6:$E$100,J19,1)+E19+I19
You can also re-use the formulas when applying Calendar Formulas 2 (Section 18), to calculate the working hours between two dates, as Calc1 and Calc2 are also common to this calculation:
Hours | Days | Start | Calc1 | Calc2 | Calc3 | Stop
7 | 0.29167 | 2000-03-15 09:30 | 9 | 0.8125 | 12 | 2000-03-15 17:30
1 | 0.041667 | 2000-03-16 16:15 | 16 | 1.4271 | 16 | 2000-03-16 17:15
Working hours between the two start dates: |  |  |  |  | 14.75 | =(E31-E30)*24
- the difference between the results of the two Calc2 formulas is the result in days, then multiply by 24 to get hours
Formulas:
Stop = INDEX('Calendar 2'!$D6:D100,[Calc3],1)-INDEX('Calendar 2'!$E6:E100,[Calc3],1)+[Calc2]+[Days]
Stop 2 = INDEX('Calendar 2'!$D6:D100,[Calc4],1)-INDEX('Calendar 2'!$E6:E100,[Calc4],1)+[Calc2]+[Days 2]

## Section 24
Repetitive Production Through Multiple Work Centres, With Calendars
Here is the schedule from Section 21 with different calendars assigned to the work centres, and the calendar calculations applied in 3 places:
- the 1st calculations take the stop of the previous operation and apply the lag duration, using the calendar of the next operation
- the 2nd calculations apply the operation duration to the start
- the 3rd calculations take the start again, re-use Calc4 and Calc5, and apply the lag duration, the result is then found by the next operation in column L
W/C | Calendar
6 | Calendar 2
7 | Calendar 1
8 | Calendar 2
The next operation can start |  |  |  | 1 | hour after the start of the previous operation (Lag) | [8 empty] | Start of first job: |  |  | 2000-03-14 06:00
[12 empty] | 1st calendar calculations |  |  |  |  | 2nd calendar calculations |  |  |  |  | 3rd calendar calculations
W/C | Calendar | Prod-uct | Op | Prod/Op | Qty | Units per Hour | Dur-ation Hours | Days | Prev Op | Prev Op Row | Start of Prev Op +Lag | Stop of Prev Op | Calc1 | Calc2 | Calc3 | Stop of Prev Op +Lag | Start | Calc4 | Calc5 | Calc6 | Stop | Calc7 | Start +Lag
6 | Calendar 2 | prod A | 1 | A/1 | 1500 | 88 | 17.0455 | 0.71023 | A/0 | #N/A | 0 | 0 | #REF! | #REF! | #REF! | 0 | 2000-03-14 06:00 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6 | Calendar 2 | prod B | 1 | B/1 | 2200 | 138 | 15.942 | 0.66425 | B/0 | #N/A | 0 | 0 | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6 | Calendar 2 | prod C | 1 | C/1 | 1900 | 238 | 7.9832 | 0.33263 | C/0 | #N/A | 0 | 0 | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 | Calendar 1 | prod A | 2 | A/2 | 1500 | 188 | 7.9787 | 0.33245 | A/1 | 19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 | Calendar 1 | prod B | 2 | B/2 | 2200 | 65 | 33.8462 | 1.4103 | B/1 | 20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 | Calendar 1 | prod C | 2 | C/2 | 1900 | 190 | 10 | 0.41667 | C/1 | 21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
8 | Calendar 2 | prod A | 3 | A/3 | 1500 | 50 | 30 | 1.25 | A/2 | 22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
8 | Calendar 2 | prod B | 3 | B/3 | 2200 | 270 | 8.1481 | 0.33951 | B/2 | 23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
8 | Calendar 2 | prod C | 3 | C/3 | 1900 | 106 | 17.9245 | 0.74686 | C/2 | 24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Formulas:
Start of Prev Op +Lag = IF(ISERROR([Prev Op Row]),0,INDEX(X1:X30,[Prev Op Row],1))
Stop of Prev Op = IF(ISERROR([Prev Op Row]),0,INDEX(V1:V30,[Prev Op Row],1))
Stop of Prev Op +Lag = IF(ISERROR([Prev Op Row]),0,INDEX(INDIRECT("'"&[Calendar]&"'!D5:D200"),[Calc3],1)-INDEX(INDIRECT("'"&[Calendar]&"'!E5:E200"),[Calc3],1)+[Calc2]+(E15/24))
Start = MAX(IF([W/C]=[W/C, row above],[Stop, row above],R15),[Start of Prev Op +Lag])

## Section 25
A Pull Schedule
Let's go back to the very simple schedule in Section 2. It says:
"If I start now (at hour zero), when will the last job stop?"
To turn it into a pull schedule, it should say:
"If all the jobs are required in 2 days (at hour 48), when do I need to start"
The answer , of course, is hour 12:
| Jobs required at hour: |  |  | 48
| Jobs | Hours | Start | Stop
| job A | 7 | 12 | 19
| job B | 5 | 19 | 24
| job C | 4 | 24 | 28
| job D | 12 | 28 | 40
| job E | 8 | 40 | 48
=E20-C20 |  |  | - the start is the stop minus the hours
=IF(ISBLANK(D21),$E$13,D21) |  |  | - if there isn't a next job, stop at the required hour, eslse stop when
the next job starts
You can see that each job is dependant on the one after it, and time cascades upwards.
What if we now changed the question to:
"If all the jobs are required in 1 day (at hour 24), when do I need to start"
Change the "Jobs required at hour" from 48 to 24, and you will see that we would need to have started at hour -12, half a day ago. In this case the nature of the question changes, and reverts back to the push question:
"If I start now (at hour zero), when will the last job stop?"
What is needed is a schedule that will handle both push and pull logic, and apply the appropriate one.

## Section 26
Push and Pull Schedule
Here is the push logic from Section 2 along side the pull logic from Section 25. By testing the 1st start of the pull, it decides which of the two to apply:
| Jobs required at hour: |  |  | 32
|  |  | Push |  | Pull |  | Apply
| Jobs | Hours | Start | Stop | Start | Stop | Start | Stop
| job A | 7 | 0 | 7 | -4 | 3 | 0 | 3
| job B | 5 | 7 | 12 | 3 | 8 | 7 | 8
| job C | 4 | 12 | 16 | 8 | 12 | 12 | 12
| job D | 12 | 16 | 28 | 12 | 24 | 16 | 24
| job E | 8 | 28 | 36 | 24 | 32 | 28 | 32
=IF(F$12<0,D12,F12) |  | - if the start of the first job on the pull schedule is -ve, apply the push
schedule, else apply the pull schedule.
You will notice that the push logic adds the hours to get the stop, whereas the pull logic works backwards, and subtracts the hours to get the start. If we want to work through a calendar, then we need a formula that will work backwards.

## Section 27
Working Backwards Through a Calendar (Calendar Formula 3)
To make a pull schedule that works through a calendar, we will need a formula that works backwards, or upwards through the calendar. Given a job stop and working hours, when will I need to start. Here is the development of the formula from Section 6, and it can be modified by changing just one sign.
Period Number | Begin | End | Working Hours | Working Hours so far (Cum)
1 | 0 | 0 | 0 | 0
2 | 8 | 10 | 2 | 2
3 | 10.25 | 13 | 2.75 | 4.75
4 | 13.5 | 15.5 | 2 | 6.75
5 | 15.75 | 18 | 2.25 | 9
6 | 19 | 22 | 3 | 12
|  | Job stops at: |  | 18.5 | (6:30 PM)
|  | Go back: |  | 8.5 | hours
Stages of the calculation:
6:30 PM is after period 5 begins | [5 empty] | 5 | =MATCH(E16,B9:B14)
6:30 PM is after period 5 ends | [5 empty] | 5 | =MATCH(E16,C9:C14)
6:30 PM lies between the beginning and end of period 6 | [5 empty] | 6 | =G21+(G21=G22)
period 6 begins at 7:00 PM | [5 empty] | 19 | =INDEX(B9:B14,G23,1)
period 6 ends at 10:00 PM | [5 empty] | 22 | =INDEX(C9:C14,G23,1)
you can stop the job at 7:00 PM because it is within a working period | [5 empty] | 19 | =MAX(G24,E16)
the number of hours from the stop of the job to the next break | [5 empty] | 3 | =G25-G26
cum hours at end of period 12 | [5 empty] | 12 | =INDEX(E9:E14,G23,1)
the job stops at cum hour 9 of the calendar | [5 empty] | 9 | =G28-G27
the job starts at cum hour 0.5 of the calendar | [5 empty] | 0.5 | =G29-E17
the job starts during period 2 | [5 empty] | 2 | =MATCH(G30,E9:E14)+1
period 2 ends 2 working hours into the calendar | [5 empty] | 2 | =INDEX(E9:E14,G31,1)
period 2 ends at hour 10 (10:00 AM) | [5 empty] | 10 | =INDEX(C9:C14,G31,1)
the job will start 1.5 hours before period 2 ends | [5 empty] | 1.5 | =G32-G30
the job will start at hour 8.5 (8:30 AM) | [5 empty] | 8.5 | =G33-G34
CHANGE THIS FROM A + TO A -
With a series of substitutions, the 15 formulas can be condensed into 4 as follows:
Calc1 | 6 | =MATCH(E16,B9:B14)+(MATCH(E16,B9:B14)=MATCH(E16,C9:C14))
Calc2 | 9 | =INDEX(E9:E14,B41,1)-(INDEX(C9:C14,B41,1)-MAX(INDEX(B9:B14,B41,1),E16))
Calc3 | 2 | =MATCH(B42-E17,E9:E14)+1
Job Stop | 8.5 | =INDEX(C9:C14,B43,1)-INDEX(E9:E14,B43,1)+B42-E17

## Section 28
Applying Calendar Formula 3 to a Pull Schedule
Here is the schedule from Section 8 again, but this time it works backwards from the stop of the last job.
| Stop of last Job: |  |  | 2000-03-17 08:30
Seq | Jobs | Hours | Days | Stop | Calc1 | Calc2 | Calc3 | Start
1 | job A | 7 | 0.29167 | 2000-03-14 16:30 | 10 | 0.8125 | 7 | 2000-03-14 08:30
2 | job C | 4 | 0.16667 | 2000-03-14 21:30 | 11 | 0.97917 | 10 | 2000-03-14 16:30
3 | job D | 5 | 0.20833 | 2000-03-15 12:45 | 13 | 1.1875 | 11 | 2000-03-14 21:30
4 | job E | 8 | 0.33333 | 2000-03-16 08:30 | 17 | 1.5208 | 13 | 2000-03-15 12:45
5 | job B | 12 | 0.5 | 2000-03-17 08:30 | 22 | 2.0208 | 17 | 2000-03-16 08:30
=MATCH(G14-D14,'Section 8'!$E$10:$E$39)+1
=INDEX('Section 8'!$D$10:$D$39,H14,1)-INDEX('Section 8'!$E$10:$E$39,H14,1)+G14-D14
Note that the calendar formulas are the same as the push schedule, except that the days in column D are subracted instead of added.
Formulas:
Stop = IF(ISBLANK([Start, row below]),E6,[Start, row below])
Start = INDEX('Section 8'!$D10:D39,[Calc3],1)-INDEX('Section 8'!$E10:E39,[Calc3],1)+[Calc2]-[Days]

## Section 29
Multiple Work Centre - Pull Schedule
To examine pull scheduling logic further we have repeated the push schedule in Section 20, and compared it with a pull version of the same schedule schedule. The pull schedule works backwards from the stop of the last job, and each job will be dependent on the next job on the work centre, and the next operation on the job.
PUSH SCHEDULE: | [10 empty] | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333
[7 empty] | Start of first job: |  | 2000-03-14 08:00
[11 empty] | 2000-03-14 |  |  | 2000-03-15 |  |  | 2000-03-16 |  |  | 2000-03-17
W/C | Jobs | Op | Job/Op | Hours | Previous Op | Previous Op Row | Stop of Previous Op | Wait hours | Start | Stop | 36599 | 36599.3333 | 36599.6667 | 36600 | 36600.3333 | 36600.6667 | 36601 | 36601.3333 | 36601.6667 | 36602 | 36602.3333 | 36602.6667 | 36603
6 | job A | 1 | A/1 | 19 | A/0 | #N/A | 1899-12-31 | 0 | 2000-03-14 08:00 | 2000-03-15 03:00 |  | 8 | 8 | 3
6 | job B | 1 | B/1 | 22 | B/0 | #N/A | 1899-12-31 | 0 | 2000-03-15 03:00 | 2000-03-16 01:00 |  |  |  | 5 | 8 | 8 | 1
6 | job C | 1 | C/1 | 17 | C/0 | #N/A | 1899-12-31 | 0 | 2000-03-16 01:00 | 2000-03-16 18:00 | [6 empty] | 7 | 8 | 2
7 | job A | 2 | A/2 | 8 | A/1 | 9 | 2000-03-15 03:00 | 19 | 2000-03-15 03:00 | 2000-03-15 11:00 |  |  |  | 5 | 3
7 | job B | 2 | B/2 | 14 | B/1 | 10 | 2000-03-16 01:00 | 14 | 2000-03-16 01:00 | 2000-03-16 15:00 | [6 empty] | 7 | 7
7 | job C | 2 | C/2 | 6 | C/1 | 11 | 2000-03-16 18:00 | 3 | 2000-03-16 18:00 | 2000-03-17 | [8 empty] | 6
8 | job A | 3 | A/3 | 13 | A/2 | 12 | 2000-03-15 11:00 | 27 | 2000-03-15 11:00 | 2000-03-16 |  |  |  |  | 5 | 8
8 | job B | 3 | B/3 | 11 | B/2 | 13 | 2000-03-16 15:00 | 15 | 2000-03-16 15:00 | 2000-03-17 02:00 | [7 empty] | 1 | 8 | 2
8 | job C | 3 | C/3 | 21 | C/2 | 14 | 2000-03-17 | 0 | 2000-03-17 02:00 | 2000-03-17 23:00 | [9 empty] | 6 | 8 | 7
PULL SCHEDULE: | [10 empty] | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333
[7 empty] | Stop of last job: |  | 2000-03-17 23:00
[11 empty] | 2000-03-14 |  |  | 2000-03-15 |  |  | 2000-03-16 |  |  | 2000-03-17
W/C | Jobs | Op | Job/Op | Hours | Next Op | Next Op Row | Start of Next Op | Wait hours | Start | Stop | 36599 | 36599.3333 | 36599.6667 | 36600 | 36600.3333 | 36600.6667 | 36601 | 36601.3333 | 36601.6667 | 36602 | 36602.3333 | 36602.6667 | 36603
6 | job A | 1 | A/1 | 19 | A/2 | 26 | 2000-03-15 17:00 | 0 | 2000-03-14 08:00 | 2000-03-15 03:00 |  | 8 | 8 | 3
6 | job B | 1 | B/1 | 22 | B/2 | 27 | 2000-03-16 01:00 | 0 | 2000-03-15 03:00 | 2000-03-16 01:00 |  |  |  | 5 | 8 | 8 | 1
6 | job C | 1 | C/1 | 17 | C/2 | 28 | 2000-03-16 20:00 | 2 | 2000-03-16 03:00 | 2000-03-16 20:00 | [6 empty] | 5 | 8 | 4
7 | job A | 2 | A/2 | 8 | A/3 | 29 | 2000-03-16 02:00 | 0 | 2000-03-15 17:00 | 2000-03-16 01:00 | [5 empty] | 7 | 1
7 | job B | 2 | B/2 | 14 | B/3 | 30 | 2000-03-16 15:00 | 0 | 2000-03-16 01:00 | 2000-03-16 15:00 | [6 empty] | 7 | 7
7 | job C | 2 | C/2 | 6 | C/3 | 31 | 2000-03-17 02:00 | 5 | 2000-03-16 20:00 | 2000-03-17 02:00 | [8 empty] | 4 | 2
8 | job A | 3 | A/3 | 13 | A/4 | #N/A | 2000-03-17 23:00 | 0 | 2000-03-16 02:00 | 2000-03-16 15:00 | [6 empty] | 6 | 7
8 | job B | 3 | B/3 | 11 | B/4 | #N/A | 2000-03-17 23:00 | 0 | 2000-03-16 15:00 | 2000-03-17 02:00 | [7 empty] | 1 | 8 | 2
8 | job C | 3 | C/3 | 21 | C/4 | #N/A | 2000-03-17 23:00 | 0 | 2000-03-17 02:00 | 2000-03-17 23:00 | [9 empty] | 6 | 8 | 7
=K31-(E31/24) | [5 empty] | - the start is the stop minus the hours
=MIN(IF(A31=A32,J32,$J$20),H31) | [5 empty] | - the stop is the earlier of: if it’s the same work centre, the start of the next job, else the stop of the last job, and the start of the next operation
Although the first start and the last stop is the same on both schedules, the work centres spend less time waiting between jobs on the pull schedule.

## Section 30
Repetitive Production Through Multiple Work Centres - Pull Schedule
Here is the schedule from Section 21 which introduced the concept of repetitive production, and sequential operations being undertaken, on a product, at the same time. Again we will compare it with a pull version of the same schedule.
PUSH SCHEDULE: | [14 empty] | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333
The next operation can start |  |  |  | 1 | hour after the start of the previous operation (Lag) |  |  |  |  | Start of first job: |  | 2000-03-14 04:00
[15 empty] | 2000-03-14 |  |  | 2000-03-15 |  |  | 2000-03-16 |  |  | 2000-03-17
W/C | Product | Op | Prod/Op | Qty | Units per Hour | Hours | Previous Op | Previous Op Row | Start of Previous Op | Stop of Previous Op | Wait hours | Start | Stop | Effective Units per Hour | 36599 | 36599.3333 | 36599.6667 | 36600 | 36600.3333 | 36600.6667 | 36601 | 36601.3333 | 36601.6667 | 36602 | 36602.3333 | 36602.6667 | 36603
6 | prod A | 1 | A/1 | 1500 | 65 | 23.0769 | A/0 | #N/A | 0 | 0 | 0 | 2000-03-14 04:00 | 2000-03-15 03:05 | 65 | 260 | 520 | 520 | 200
6 | prod B | 1 | B/1 | 2200 | 60 | 36.6667 | B/0 | #N/A | 0 | 0 | 0 | 2000-03-15 03:05 | 2000-03-16 15:45 | 60 |  |  |  | 295.3846 | 480 | 480 | 480 | 464.6154
6 | prod C | 1 | C/1 | 1900 | 75 | 25.3333 | C/0 | #N/A | 0 | 0 | 0 | 2000-03-16 15:45 | 2000-03-17 17:05 | 75 | [7 empty] | 19.2308 | 600 | 600 | 600 | 80.7692
7 | prod A | 2 | A/2 | 1500 | 105 | 14.2857 | A/1 | 9 | 2000-03-14 05:00 | 2000-03-15 04:05 | 1 | 2000-03-14 05:00 | 2000-03-15 04:05 | 65 | 195 | 520 | 520 | 265
7 | prod B | 2 | B/2 | 2200 | 95 | 23.1579 | B/1 | 10 | 2000-03-15 04:05 | 2000-03-16 16:45 | 0 | 2000-03-15 04:05 | 2000-03-16 16:45 | 60 |  |  |  | 235.3846 | 480 | 480 | 480 | 480 | 44.6154
7 | prod C | 2 | C/2 | 1900 | 110 | 17.2727 | C/1 | 11 | 2000-03-16 16:45 | 2000-03-17 18:05 | 0 | 2000-03-16 16:45 | 2000-03-17 18:05 | 75 | [8 empty] | 544.2308 | 600 | 600 | 155.7692
8 | prod A | 3 | A/3 | 1500 | 80 | 18.75 | A/2 | 12 | 2000-03-14 06:00 | 2000-03-15 05:05 | 2 | 2000-03-14 06:00 | 2000-03-15 05:05 | 65 | 130 | 520 | 520 | 330
8 | prod B | 3 | B/3 | 2200 | 85 | 25.8824 | B/2 | 13 | 2000-03-15 05:05 | 2000-03-16 17:45 | 0 | 2000-03-15 05:05 | 2000-03-16 17:45 | 60 |  |  |  | 175.3846 | 480 | 480 | 480 | 480 | 104.6154
8 | prod C | 3 | C/3 | 1900 | 95 | 20 | C/2 | 14 | 2000-03-16 17:45 | 2000-03-17 19:05 | 0 | 2000-03-16 17:45 | 2000-03-17 19:05 | 75 | [8 empty] | 469.2308 | 600 | 600 | 230.7692
PULL SCHEDULE: | [14 empty] | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333
The next operation can start |  |  |  | 1 | hour after the start of the previous operation (Lag) |  |  |  |  | Stop of last job: |  | 2000-03-17 19:05
[15 empty] | 2000-03-14 |  |  | 2000-03-15 |  |  | 2000-03-16 |  |  | 2000-03-17
W/C | Product | Op | Prod/Op | Qty | Units per Hour | Hours | Next Op | Next Op Row | Start of Next Op | Stop of Next Op | Wait hours | Start | Stop | Effective Units per Hour | 36599 | 36599.3333 | 36599.6667 | 36600 | 36600.3333 | 36600.6667 | 36601 | 36601.3333 | 36601.6667 | 36602 | 36602.3333 | 36602.6667 | 36603
6 | prod A | 1 | A/1 | 1500 | 65 | 23.0769 | A/2 | 26 | 2000-03-15 00:27 | 2000-03-15 19:12 | 0 | 2000-03-14 04:00 | 2000-03-15 03:05 | 65 | 260 | 520 | 520 | 200
6 | prod B | 1 | B/1 | 2200 | 60 | 36.6667 | B/2 | 27 | 2000-03-15 19:12 | 2000-03-16 21:05 | 0 | 2000-03-15 03:05 | 2000-03-16 15:45 | 60 |  |  |  | 295.3846 | 480 | 480 | 480 | 464.6154
6 | prod C | 1 | C/1 | 1900 | 75 | 25.3333 | C/2 | 28 | 2000-03-16 21:05 | 2000-03-17 17:05 | 0 | 2000-03-16 15:45 | 2000-03-17 17:05 | 75 | [7 empty] | 19.2308 | 600 | 600 | 600 | 80.7692
7 | prod A | 2 | A/2 | 1500 | 105 | 14.2857 | A/3 | 29 | 2000-03-15 01:27 | 2000-03-15 20:12 | 0 | 2000-03-15 01:27 | 2000-03-15 20:12 | 80 |  |  |  | 524.4344 | 640 | 335.5656
7 | prod B | 2 | B/2 | 2200 | 95 | 23.1579 | B/3 | 30 | 2000-03-15 20:12 | 2000-03-16 22:05 | 0 | 2000-03-15 20:12 | 2000-03-16 22:05 | 85 | [5 empty] | 323.4615 | 680 | 680 | 516.5385
7 | prod C | 2 | C/2 | 1900 | 110 | 17.2727 | C/3 | 31 | 2000-03-16 22:05 | 2000-03-17 18:05 | 0 | 2000-03-16 22:05 | 2000-03-17 18:05 | 95 | [8 empty] | 182.6923 | 760 | 760 | 197.3077
8 | prod A | 3 | A/3 | 1500 | 80 | 18.75 | A/4 | #N/A | 2000-03-17 19:05 | 2000-03-17 19:05 | 0 | 2000-03-15 02:27 | 2000-03-15 21:12 | 80 |  |  |  | 444.4344 | 640 | 415.5656
8 | prod B | 3 | B/3 | 2200 | 85 | 25.8824 | B/4 | #N/A | 2000-03-17 19:05 | 2000-03-17 19:05 | 0 | 2000-03-15 21:12 | 2000-03-16 23:05 | 85 | [5 empty] | 238.4615 | 680 | 680 | 601.5385
8 | prod C | 3 | C/3 | 1900 | 95 | 20 | C/4 | #N/A | 2000-03-17 19:05 | 2000-03-17 19:05 | 0 | 2000-03-16 23:05 | 2000-03-17 19:05 | 95 | [8 empty] | 87.6923 | 760 | 760 | 292.3077
[5 empty] | =MIN(N31-(G31/24),J31-(E$20/24)) |  |  |  | - the start is: the earlier of the stop minus the hours, and one hour before the start of the next operation
[5 empty] | =IF(A31=A32,M32,K31) |  |  |  | - the stop is: the start of the next job on the work centre, if there is one, else the stop of the next operation on the job.
Again the entire schedule stops and starts at the same times, but the work centres don't start until they need to, and the effective run rates, in units per hour, are higher.

## Section 31
Repetitive Production, Multiple Work Centres, Pull Schedule, With Calendars
In Sectin 24 we took a push schedule and applied calendar calculations to it. Here is the pull schedule from Section 30 with different calendars assigned to the work centres, and the calendar calculations applied in 3 places:
- the 1st calculations take the start of the next operation and subtract the lag duration, using the calendar of the previous operation
- the 2nd calculations apply the operation duration to the stop, to derive the start
- the 3rd calculations take the stop again, re-use Calc4 and Calc5, and subtract the lag duration, the result is then found by the previous operation in column L
W/C | Calendar
6 | Calendar 2
7 | Calendar 1
8 | Calendar 2
The next operation can start |  |  |  | 1 | hour after the start of the previous operation (Lag) | [11 empty] | Stop of last job: |  |  |  | 2000-03-27 19:05
[12 empty] | 1st calendar calculations |  |  |  |  | 2nd calendar calculations |  |  |  |  | 3rd calendar calculations
W/C | Calendar | Prod-uct | Op | Prod/Op | Qty | Units per Hour | Dur-ation Hours | Days | Next Op | Next Op Row | Stop of Next Op | Start of Next Op | Calc1 | Calc2 | Calc3 | Start of Next Op -Lag | Stop | Calc4 | Calc5 | Calc6 | Start | Calc7 | Stop -Lag
6 | Calendar 2 | prod A | 1 | A/1 | 1500 | 65 | 23.0769 | 0.96154 | A/2 | 22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6 | Calendar 2 | prod B | 1 | B/1 | 2200 | 60 | 36.6667 | 1.5278 | B/2 | 23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6 | Calendar 2 | prod C | 1 | C/1 | 1900 | 75 | 25.3333 | 1.0556 | C/2 | 24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 | Calendar 1 | prod A | 2 | A/2 | 1500 | 105 | 14.2857 | 0.59524 | A/3 | 25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 | Calendar 1 | prod B | 2 | B/2 | 2200 | 95 | 23.1579 | 0.96491 | B/3 | 26 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 | Calendar 1 | prod C | 2 | C/2 | 1900 | 110 | 17.2727 | 0.7197 | C/3 | 27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
8 | Calendar 2 | prod A | 3 | A/3 | 1500 | 80 | 18.75 | 0.78125 | A/4 | #N/A | 2000-03-27 19:05 | 2000-03-27 19:05 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
8 | Calendar 2 | prod B | 3 | B/3 | 2200 | 85 | 25.8824 | 1.0784 | B/4 | #N/A | 2000-03-27 19:05 | 2000-03-27 19:05 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
8 | Calendar 2 | prod C | 3 | C/3 | 1900 | 95 | 20 | 0.83333 | C/4 | #N/A | 2000-03-27 19:05 | 2000-03-27 19:05 | #REF! | #REF! | #REF! | #REF! | 2000-03-27 19:05 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Formulas:
Stop of Next Op = IF(ISERROR([Next Op Row]),V15,INDEX(X1:X28,[Next Op Row],1))
Start of Next Op = IF(ISERROR([Next Op Row]),V15,INDEX(V1:V28,[Next Op Row],1))
Stop = IF([W/C]=[W/C, row below],[Start, row below],[Stop of Next Op])

## Section 32
Push Pull Push - 3 Pass Logic
In Section 26 we had a series of jobs that were all required at the same time, but here we consider jobs with different required times. We will start with a simple example of Job A required in 24 hours, and Job B required 48 hours from now. The objective is to try and meet the due date of each job, but to start each job just in time. The logic works in 3 passes, and "shuffles" the jobs taking into consideration the following:
- the start of the schedule (hour zero)
- the length of the job in hours
- when the job is due
- the stop of the previous job
- the start of the next job
|  |  | Push 1 |  | Pull |  | Push 2 |  |  | Day 1 |  |  | Day 2
Jobs | Hours | Due | Start | Stop | Start | Stop | Start | Stop | 0 | 8 | 16 | 24 | 32 | 40 | 48 | 56
In the first pass job A starts now, and job B starts immediately after that:
job A | 32 | 24 | 0 | 32 | bar: Day 1 8 to Day 2 32
job B | 8 | 48 | 32 | 40 | bar: Day 2 40
In the second pass each job stops when it is due, so job A would need to have started 8 hours ago:
job A | 32 | 24 | 0 | 32 | -8 | 24 | bar: 0 to Day 1 24
job B | 8 | 48 | 32 | 40 | 40 | 48 | bar: Day 2 48
The third pass pushes job A later so that it starts at hour zero:
job A | 32 | 24 | 0 | 32 | -8 | 24 | 0 | 32 | bar: Day 1 8 to Day 2 32
job B | 8 | 48 | 32 | 40 | 40 | 48 | 40 | 48 | bar: Day 2 48
Here are some other examples:
job A | 32 | 24 | 0 | 32 | -8 | 24 | 0 | 32 | bar: Day 1 8 to Day 2 32
job B | 24 | 48 | 32 | 56 | 24 | 48 | 32 | 56 | bar: Day 2 40 to Day 2 56
job A | 16 | 24 | 0 | 16 | 8 | 24 | 8 | 24 | bar: Day 1 16 to Day 1 24
job B | 16 | 48 | 16 | 32 | 32 | 48 | 32 | 48 | bar: Day 2 40 to Day 2 48
job A | 8 | 24 | 0 | 8 | 8 | 16 | 8 | 16 | bar: Day 1 16
job B | 32 | 48 | 8 | 40 | 16 | 48 | 16 | 48 | bar: Day 1 24 to Day 2 48
job A | 16 | 24 | 0 | 16 | -8 | 8 | 0 | 16 | bar: Day 1 8 to Day 1 16
job B | 40 | 48 | 16 | 56 | 8 | 48 | 16 | 56 | bar: Day 1 24 to Day 2 56
=MIN(C34,F35) |  |  |  | - pull stop is the earlier of the due time or the start of the next job
=MAX(D34,F34,I33) |  |  |  | - push 2 start is the later of: |  |  |  |  | 0: the earliest start
the push start
the stop of the previous job
=H34+B34 |  |  |  | - push 2 stop is the start plus hours

## Section 33
Multiple Work Centre - 3 Pass Schedule
Here we apply the 3 pass logic set out in Section 31 to jobs that pass through multiple work centres. The logic that applies to the Push 1 part of the schedule is explained in Section 20. The Pull part is in Section 29, but has been modified to cope with Due time. This example uses hurs rather than Julian dates, simply because we can make the columns narrower this way. The Push 2 logic is the same as in Section 32, except that the start is subject to an additional constraint, the stop of the previous operation. So now the scheduling of a job takes 7 things into consideration:
- the start of the schedule (hour zero)
- the length of the job in hours
- when the job is due
- the stop of the previous job on the work centre
- the start of the next job on the work centre
- the stop of the previous operation on the job
- the start of the next next operation on the job
[6 empty] | Push 1 |  |  |  |  | Pull |  |  |  |  | Push 2 |  |  |  | Day 1 |  |  | Day 2 |  |  | Day 3 |  |  | Day 4
W/C | Jobs | Op | Job/Op | Hours | Due | Prev. Op | Prev. Op Row | Stop of Prev. Op | Start | Stop | Next Op | Next Op Row | Start of Next Op | Start | Stop | Stop of Prev. Op | Start | Stop | 0 | 8 | 16 | 24 | 32 | 40 | 48 | 56 | 64 | 72 | 80 | 88 | 96
6 | job A | 1 | A/1 | 16 |  | A/0 | #N/A | 0 | 0 | 16 | A/2 | 18 | 0 | -16 | 0 | 0 | 0 | 16 | bar: Day 1 8 to Day 1 16
6 | job B | 1 | B/1 | 16 |  | B/0 | #N/A | 0 | 16 | 32 | B/2 | 19 | 32 | 16 | 32 | 0 | 16 | 32 | bar: Day 1 24 to Day 2 32
6 | job C | 1 | C/1 | 8 |  | C/0 | #N/A | 0 | 32 | 40 | C/2 | 20 | 72 | 64 | 72 | 0 | 64 | 72 | bar: Day 3 72
7 | job A | 2 | A/2 | 8 |  | A/1 | 15 | 16 | 16 | 24 | A/3 | 21 | 8 | 0 | 8 | 16 | 16 | 24 | bar: Day 1 24
7 | job B | 2 | B/2 | 32 |  | B/1 | 16 | 32 | 32 | 64 | B/3 | 22 | 64 | 32 | 64 | 32 | 32 | 64 | bar: Day 2 40 to Day 3 64
7 | job C | 2 | C/2 | 8 |  | C/1 | 17 | 40 | 64 | 72 | C/3 | 23 | 80 | 72 | 80 | 72 | 72 | 80 | bar: Day 4 80
8 | job A | 3 | A/3 | 16 | 24 | A/2 | 18 | 24 | 24 | 40 | A/4 | #N/A | 24 | 8 | 24 | 24 | 24 | 40 | bar: Day 2 32 to Day 2 40
8 | job B | 3 | B/3 | 8 | 72 | B/2 | 19 | 64 | 64 | 72 | B/4 | #N/A | 72 | 64 | 72 | 64 | 64 | 72 | bar: Day 3 72
8 | job C | 3 | C/3 | 16 | 96 | C/2 | 20 | 72 | 72 | 88 | C/4 | #N/A | 96 | 80 | 96 | 80 | 80 | 96 | bar: Day 4 88 to Day 4 96
These are the formulas that are different:
[6 empty] | =IF(ISERROR(M23),F23,INDEX(O$1:O$28,M23,1)) | [6 empty] | - if there isn't a next operation put in the time due, else find the start of the next op in coumn O
[6 empty] | =MIN(IF(A23=A24,O24,999),N23) | [6 empty] | - the stop is the earlier of: the start of the next job on the work centre if there is one, else the start of the next op (or the time due)
[6 empty] | =MAX(J23,O23,Q23,IF(A23=A22,S22,0)) | [6 empty] | - the start is the later of: |  |  | earliest (push 1) start
latest (pull) start
stop of the previous operation
stop of the previous job on the work centre, if there is one
Try changing the hours and due figures, and see how the schedule behaves.

## Section 34
Repetitive Production Through Multiple Work Centres - 3 Pass Schedule
Applying the 3 pass logic to this case becomes more complex still. The Push 1 logic is explained in Section 21, and the pull logic from Section 30 has been modified to cope with the time Due. The list of things taken into consideration when scheduling a job now grows to 10:
- the start of the schedule (hour zero)
- the length of the job in hours
- when the job is due
- the stop of the previous job on the work centre
- the start of the next job on the work centre
- the 1 hour that the next operation lags behind the previous operation
- the start of the previous operation on the job
- the stop of the previous operation on the job
- the start of the next next operation on the job
- the stop of the next next operation on the job
The next operation can start |  |  |  |  | 1 | hour after the start of the previous operation (Lag) | [18 empty] | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
[8 empty] | Push 1 | [5 empty] | Pull | [5 empty] | Push 2 |  |  |  |  | Day 1 |  |  | Day 2 |  |  | Day 3 |  |  | Day 4
W/C | Prod-uct | Op | Prod/Op | Qty | Due | Units per Hour | Hours | Prev Op | Prev Op Row | Start of Prev Op | Stop of Prev Op | Start | Stop | Next Op | Next Op Row | Start of Next Op | Stop of Next Op | Start | Stop | Start of Prev Op | Stop of Prev Op | Start | Stop | Effective Units per Hour | 0 | 8 | 16 | 24 | 32 | 40 | 48 | 56 | 64 | 72 | 80 | 88 | 96
6 | prod A | 1 | A/1 | 1500 |  | 88.2353 | 17 | A/0 | #N/A | -1 | -1 | 0 | 17 | A/2 | 22 | -8 | 22 | -8 | 22 | -1 | -1 | 0 | 17 | 88.2353 | Day 1 0: 705.8824; Day 1 8: 705.8824; Day 1 16: 88.2353
6 | prod B | 1 | B/1 | 2200 |  | 137.5 | 16 | B/0 | #N/A | -1 | -1 | 17 | 33 | B/2 | 23 | 36 | 70 | 36 | 70 | -1 | -1 | 36 | 52 | 137.5 | Day 2 32: 550; Day 2 40: 1100; Day 3 48: 550
6 | prod C | 1 | C/1 | 1900 |  | 237.5 | 8 | C/0 | #N/A | -1 | -1 | 33 | 41 | C/2 | 24 | 76 | 94 | 76 | 94 | -1 | -1 | 76 | 84 | 237.5 | Day 4 72: 950; Day 4 80: 950
7 | prod A | 2 | A/2 | 1500 |  | 187.5 | 8 | A/1 | 19 | 1 | 18 | 1 | 18 | A/3 | 25 | -7 | 23 | -7 | 23 | 1 | 18 | 1 | 18 | 88.2353 | Day 1 0: 617.6471; Day 1 8: 705.8824; Day 1 16: 176.4706
7 | prod B | 2 | B/2 | 2200 |  | 64.7059 | 34 | B/1 | 20 | 18 | 34 | 18 | 52 | B/3 | 26 | 63 | 71 | 37 | 71 | 37 | 53 | 37 | 71 | 64.7059 | Day 2 32: 194.1176; Day 2 40: 517.6471; Day 3 48: 517.6471; Day 3 56: 517.6471; Day 3 64: 452.9412
7 | prod C | 2 | C/2 | 1900 |  | 190 | 10 | C/1 | 21 | 34 | 42 | 52 | 62 | C/3 | 27 | 77 | 95 | 77 | 95 | 77 | 85 | 77 | 87 | 190 | Day 4 72: 570; Day 4 80: 1330
8 | prod A | 3 | A/3 | 1500 | 24 | 50 | 30 | A/2 | 22 | 2 | 19 | 2 | 32 | A/4 | #N/A | 24 | 24 | -6 | 24 | 2 | 19 | 2 | 32 | 50 | Day 1 0: 300; Day 1 8: 400; Day 1 16: 400; Day 2 24: 400
8 | prod B | 3 | B/3 | 2200 | 72 | 275 | 8 | B/2 | 23 | 19 | 53 | 32 | 53 | B/4 | #N/A | 72 | 72 | 64 | 72 | 38 | 72 | 64 | 72 | 275 | Day 3 64: 2200
8 | prod C | 3 | C/3 | 1900 | 96 | 105.5556 | 18 | C/2 | 24 | 53 | 63 | 53 | 71 | C/4 | #N/A | 96 | 96 | 78 | 96 | 78 | 88 | 78 | 96 | 105.5556 | Day 4 72: 211.1111; Day 4 80: 844.4444; Day 4 88: 844.4444
[5 empty] | =IF(ISERROR(J27),-F$16,INDEX(X$1:X$30,J27,1)+F$16) | [6 empty] | - if there isn't a previous operation return 1 hour before the start of the schedule, else find the stop of the previous operation in column X
[5 empty] | =MAX(M27,S27,U27,IF(A27=A26,X26,0)) | [6 empty] | - the start is the later of: |  |  |  | earliest (push 1) start
latest (pull) start
the start of the previous operation (plus 1 hour)
stop of the previous job on the work centre, if there is one
[5 empty] | =MAX(W27+H27,V27) | [6 empty] | - the stop is the later of, the start plus the hours, and the stop of the previous operation (plus 1 hour)

## Section 35
3 Pass Schedule With a Calendar
All the calculations in the 3 pass schedules in Sections 33 and 34 have been done on the basis of hours into the schedule. If all work centres work 24 hours a day, 7 days a week, then it would be straightforward to convert the start and stop times to Julian dates. However, if the work centres follow a calendar, then we need to apply the calendar formulas. We start with the start and stop from push 2 of Section 34 (columns W and X), and apply the formulas set out in Section 10.
|  | Start of first job: |  |  | 2000-03-14 08:30
W/C | Prod-uct | Start hour | Stop hour | Days | Start Date | Calc1 | Calc2 | Calc3 | Stop
6 | prod A | 0 | 17 | 0.70833 | 2000-03-14 08:30 | 5 | 1.1042 | 12 | 2000-03-15 17:30
6 | prod B | 36 | 52 | 0.66667 | 2000-03-15 17:30 | 12 | 1.7708 | 19 | 2000-03-17 15:15
6 | prod C | 76 | 84 | 0.33333 | 2000-03-17 15:15 | 19 | 2.1042 | 23 | 2000-03-20 15:15
7 | prod A | 1 | 18 | 0.70833 | 2000-03-14 09:30 | 5 | 1.1458 | 13 | 2000-03-16 08:30
7 | prod B | 37 | 71 | 1.4167 | 2000-03-16 08:30 | 13 | 2.5625 | 28 | 2000-03-21 17:30
7 | prod C | 77 | 87 | 0.41667 | 2000-03-21 17:30 | 28 | 2.9792 | 33 | 2000-03-23 08:30
8 | prod A | 2 | 32 | 1.25 | 2000-03-14 10:30 | 6 | 1.7187 | 19 | 2000-03-17 14:00
8 | prod B | 64 | 72 | 0.33333 | 2000-03-17 14:00 | 19 | 2.0521 | 23 | 2000-03-20 14:00
8 | prod C | 78 | 96 | 0.75 | 2000-03-20 14:00 | 23 | 2.8021 | 31 | 2000-03-22 14:00
=(D17-C17)/24 |  |  | - the duration of the operation is re-established from the stop and start hours, as it is not always the same as the hours (Section 30, column H)
Formulas:
Start Date = IF([W/C]=[W/C, row above],[Stop, row above],F6+([Start hour]/24))
Stop = INDEX('Calendar 2'!$D6:D200,[Calc3],1)-INDEX('Calendar 2'!$E6:E200,[Calc3],1)+[Calc2]

## Section 36
3 Pass Schedule With Multiple Calendars
Each work centre may adhere to a different calendar, as would be the case if the constraint work centre was scheduled to work overtime or weekends. In this case, 3 pass scheduling, using hours into the schedule, won't work because for example, hour 17 on Work Centre 6 will translate into 3/15/00 5:30 PM according to Calendar 2, but if Work Centre 7 works to Calendar 1, hour 17 may translate into a completely different date and time. Every instance were a duration is added or subtracted from a date and time, to get to another date and time, will have to pass through the calendar formulas. That's an awful lot of formulas, but lets start by adding the calendar formulas to the schedule in Section 33:
W/C | Calendar
6 | Calendar 2
7 | Calendar 1
8 | Calendar 2
[8 empty] | Start of first job: |  |  | 2000-03-14 06:00
[8 empty] | Push 1 | [7 empty] | Pull | [7 empty] | Push 2
W/C | Calendar | Jobs | Op | Job/Op | Hours | Days | Due | Prev. Op | Prev. Op Row | Stop of Prev. Op | Start | Calc1 | Calc2 | Calc3 | Stop | Next Op | Next Op Row | Start of Next Op | Stop | Calc4 | Calc5 | Calc6 | Start | Stop of Prev. Op | Start | Calc7 | Calc8 | Calc9 | Stop
6 | Calendar 2 | job A | 1 | A/1 | 6 | 0.25 |  | A/0 | #N/A | 0 | 2000-03-14 06:00 | #REF! | #REF! | #REF! | #REF! | A/2 | 18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
6 | Calendar 2 | job B | 1 | B/1 | 12 | 0.5 |  | B/0 | #N/A | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | B/2 | 19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
6 | Calendar 2 | job C | 1 | C/1 | 8 | 0.33333 |  | C/0 | #N/A | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | C/2 | 20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
7 | Calendar 1 | job A | 2 | A/2 | 8 | 0.33333 |  | A/1 | 15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | A/3 | 21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 | Calendar 1 | job B | 2 | B/2 | 20 | 0.83333 |  | B/1 | 16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | B/3 | 22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 | Calendar 1 | job C | 2 | C/2 | 8 | 0.33333 |  | C/1 | 17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | C/3 | 23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
8 | Calendar 2 | job A | 3 | A/3 | 16 | 0.66667 | 2000-03-20 11:00 | A/2 | 18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | A/4 | #N/A | 2000-03-20 11:00 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
8 | Calendar 2 | job B | 3 | B/3 | 8 | 0.33333 | 2000-03-21 15:00 | B/2 | 19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | B/4 | #N/A | 2000-03-21 15:00 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
8 | Calendar 2 | job C | 3 | C/3 | 16 | 0.66667 | 2000-03-22 08:00 | C/2 | 20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | C/4 | #N/A | 2000-03-22 08:00 | 2000-03-22 08:00 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Formulas:
Stop of Prev. Op = IF(ISERROR([Prev. Op Row]),0,INDEX(P1:P28,[Prev. Op Row],1))
Start = MAX(IF([W/C]=[W/C, row above],[Stop, row above],L11),[Stop of Prev. Op])
Push 2 = IF(ISERROR([Prev. Op Row]),0,INDEX(AD1:AD28,[Prev. Op Row],1))
Start of Next Op = IF(ISERROR([Next Op Row]),[Due],INDEX(X1:X28,[Next Op Row],1))
Stop = MIN(IF([W/C]=[W/C, row below],[Start, row below],99999),[Start of Next Op])

## Section 37
Repetitive Production, 3 Pass Schedule With Multiple Calendars
Here we have taken the schedule in Section 34, and applied calendar calculations to it. You can see that it takes 53 columns to do it! However, we have built up to this in stages, In Section 24 we added the calendar formulas to a push schedule, in Section 31 to a pull schedule, and here we have put it all together.
W/C | Calendar
6 | Calendar 2
7 | Calendar 1
8 | Calendar 2
The next operation can start |  |  |  | 1 | hour after the start of the previous operation (Lag) | [9 empty] | Start of first job: |  |  | 2000-03-14 06:00
[10 empty] | Push 1 | [14 empty] | Pull | [14 empty] | Push 2
W/C | Calendar | Prod-uct | Op | Prod/Op | Qty | Units per Hour | Dur-ation Hours | Days | Due | Prev Op | Prev Op Row | Start of Prev Op +Lag | Stop of Prev Op | Calc1 | Calc2 | Calc3 | Stop of Prev Op +Lag | Start | Calc4 | Calc5 | Calc6 | Stop | Calc7 | Start +Lag | Next Op | Next Op Row | Stop of Next Op -Lag | Start of Next Op | Calc8 | Calc9 | Calc10 | Start of Next Op -Lag | Stop | Calc11 | Calc12 | Calc13 | Start | Calc14 | Stop -Lag | Start of Prev Op +Lag | Stop of Prev Op | Calc15 | Calc16 | Calc17 | Stop of Prev Op +Lag | Start | Calc18 | Calc19 | Calc20 | Stop | Calc21 | Start +Lag
6 | Calendar 2 | prod A | 1 | A/1 | 1500 | 88 | 17.0455 | 0.71023 |  | A/0 | #N/A | 0 | 0 | #REF! | #REF! | #REF! | 0 | 2000-03-14 06:00 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | A/2 | 22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6 | Calendar 2 | prod B | 1 | B/1 | 2200 | 138 | 15.942 | 0.66425 |  | B/0 | #N/A | 0 | 0 | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | B/2 | 23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6 | Calendar 2 | prod C | 1 | C/1 | 1900 | 238 | 7.9832 | 0.33263 |  | C/0 | #N/A | 0 | 0 | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | C/2 | 24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 | Calendar 1 | prod A | 2 | A/2 | 1500 | 188 | 7.9787 | 0.33245 |  | A/1 | 19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | A/3 | 25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 | Calendar 1 | prod B | 2 | B/2 | 2200 | 65 | 33.8462 | 1.4103 |  | B/1 | 20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | B/3 | 26 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 | Calendar 1 | prod C | 2 | C/2 | 1900 | 190 | 10 | 0.41667 |  | C/1 | 21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | C/3 | 27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
8 | Calendar 2 | prod A | 3 | A/3 | 1500 | 50 | 30 | 1.25 | 2000-03-21 11:00 | A/2 | 22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | A/4 | #N/A | 2000-03-21 11:00 | 2000-03-21 11:00 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
8 | Calendar 2 | prod B | 3 | B/3 | 2200 | 270 | 8.1481 | 0.33951 | 2000-03-22 15:00 | B/2 | 23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | B/4 | #N/A | 2000-03-22 15:00 | 2000-03-22 15:00 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
8 | Calendar 2 | prod C | 3 | C/3 | 1900 | 106 | 17.9245 | 0.74686 | 2000-03-23 08:00 | C/2 | 24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | C/4 | #N/A | 2000-03-23 08:00 | 2000-03-23 08:00 | #REF! | #REF! | #REF! | #REF! | 2000-03-23 08:00 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Formulas:
Start of Prev Op +Lag = IF(ISERROR([Prev Op Row]),0,INDEX(Y1:Y30,[Prev Op Row],1))
Stop of Prev Op = IF(ISERROR([Prev Op Row]),0,INDEX(W1:W30,[Prev Op Row],1))
Stop of Prev Op = IF(ISERROR([Prev Op Row]),0,INDEX(AY1:AY30,[Prev Op Row],1))
Stop of Prev Op +Lag = IF(ISERROR([Prev Op Row]),0,INDEX(INDIRECT("'"&[Calendar]&"'!D5:D200"),[Calc3],1)-INDEX(INDIRECT("'"&[Calendar]&"'!E5:E200"),[Calc3],1)+[Calc2]+(E15/24))
Start = MAX(IF([W/C]=[W/C, row above],[Stop, row above],S15),[Start of Prev Op +Lag])
Push 2 = IF(ISERROR([Prev Op Row]),0,INDEX(BA1:BA30,[Prev Op Row],1))
Stop of Next Op -Lag = IF(ISERROR([Next Op Row]),[Due],INDEX(AN1:AN28,[Next Op Row],1))
Start of Next Op = IF(ISERROR([Next Op Row]),[Due],INDEX(AL1:AL28,[Next Op Row],1))
Stop = IF([W/C]=[W/C, row below],[Start, row below],[Stop of Next Op -Lag])

## Section 38
Project Scheduling
So far our examples have related to production activities, where a job's dependancies are implied, such as the previous job on a work centre, or a previous operation on a job. With a project the pattern of dependancies have to be spelled out. Here is an example:
Activity | Duration secs. | Depend-ency 1 | Depend-ency 2 | Dep. Stop 1 | Dep. Stop 2 | Start | Stop
wake up | 30 |  |  | 0 | 0 | 0 | 30
walk to kitchen | 15 | 6 |  | 30 | 0 | 30 | 45
fill kettle | 20 | 7 |  | 45 | 0 | 45 | 65
boil water | 180 | 8 |  | 65 | 0 | 65 | 245
put bread in toaster | 20 | 8 |  | 65 | 0 | 65 | 85
toast bread | 150 | 10 |  | 85 | 0 | 85 | 235
walk to bathroom | 15 | 10 |  | 85 | 0 | 85 | 100
turn on bath taps | 10 | 12 |  | 100 | 0 | 100 | 110
fill bath | 180 | 13 |  | 110 | 0 | 110 | 290
brush teeth | 60 | 12 |  | 100 | 0 | 100 | 160
shave | 80 | 15 |  | 160 | 0 | 160 | 240
remove night clothes | 10 | 16 |  | 240 | 0 | 240 | 250
get into bath | 5 | 17 | 14 | 250 | 290 | 290 | 295
wash body | 90 | 18 |  | 295 | 0 | 295 | 385
shampoo hair | 40 | 19 |  | 385 | 0 | 385 | 425
get dried | 30 | 20 |  | 425 | 0 | 425 | 455
put on underwear | 10 | 21 |  | 455 | 0 | 455 | 465
put on shirt and trousers | 30 | 22 |  | 465 | 0 | 465 | 495
put on tie | 30 | 23 |  | 495 | 0 | 495 | 525
walk to kitchen | 15 | 23 |  | 495 | 0 | 495 | 510
lay table | 60 | 24 | 25 | 525 | 510 | 525 | 585
make tea | 90 | 26 | 9 | 585 | 245 | 585 | 675
spread toast | 60 | 27 | 11 | 675 | 235 | 675 | 735
eat breakfast | 300 | 27 | 28 | 675 | 735 | 735 | 1035
Total Duration: | 0:17 | h:mm:ss
=IF(C28,INDIRECT("H"&C28),0) |  | - find the time that the dependency stops, at its row number
=MAX(E28,F28) |  | - the activity starts at the later of the two dependencies
=G28+B28 |  | - the stop is the start plus the duration
Please excuse the fact that this example is not politically correct and gender neutral. Please note however, that you brush your teeth whilst turning on the bath taps, but you shouln't have bothered because you stand there naked waiting for the bath to fill. You also put on your tie while walking to the kitchen, which saves you 15 seconds.

## Section 39
Critical Path Analysis
The shaded activities, below, are on the critical path. An increase in duration of tese would extend the entire project, whereas non-critical activities have some "float". Push logic calculates the earliest start of each activity, and the end time of the project, then working back from this, pull logic calculates the latest start. The first step is to determine for each activity, the next activities that are dependent on it.
Row | Activity | Dur. Secs | Dep 1 | Dep 2 | Dep. Stop 1 | Dep. Stop 2 | Push Start | Push Stop | Next 1 | Next 2 | Next 3 | Next start 1 | Next start 2 | Next start 3 | Pull Stop | Pull Start | Float
6 | wake up | 30 |  |  | 0 | 0 | 0 | 30 | 7 | #N/A | #N/A | 30 | 1035 | 1035 | 30 | 0 | 0
7 | walk to kitchen | 15 | 6 |  | 30 | 0 | 30 | 45 | 8 | #N/A | #N/A | 45 | 1035 | 1035 | 45 | 30 | 0
8 | fill kettle | 20 | 7 |  | 45 | 0 | 45 | 65 | 9 | 10 | #N/A | 405 | 65 | 1035 | 65 | 45 | 0
9 | boil water | 180 | 8 |  | 65 | 0 | 65 | 245 | #N/A | #N/A | 27 | 1035 | 1035 | 585 | 585 | 405 | 340
10 | put bread in toaster | 20 | 8 |  | 65 | 0 | 65 | 85 | 11 | 12 | #N/A | 525 | 85 | 1035 | 85 | 65 | 0
11 | toast bread | 150 | 10 |  | 85 | 0 | 85 | 235 | #N/A | #N/A | 28 | 1035 | 1035 | 675 | 675 | 525 | 440
12 | walk to bathroom | 15 | 10 |  | 85 | 0 | 85 | 100 | 13 | 15 | #N/A | 100 | 140 | 1035 | 100 | 85 | 0
13 | turn on bath taps | 10 | 12 |  | 100 | 0 | 100 | 110 | 14 | #N/A | #N/A | 110 | 1035 | 1035 | 110 | 100 | 0
14 | fill bath | 180 | 13 |  | 110 | 0 | 110 | 290 | #N/A | #N/A | 18 | 1035 | 1035 | 290 | 290 | 110 | 0
15 | brush teeth | 60 | 12 |  | 100 | 0 | 100 | 160 | 16 | #N/A | #N/A | 200 | 1035 | 1035 | 200 | 140 | 40
16 | shave | 80 | 15 |  | 160 | 0 | 160 | 240 | 17 | #N/A | #N/A | 280 | 1035 | 1035 | 280 | 200 | 40
17 | remove night clothes | 10 | 16 |  | 240 | 0 | 240 | 250 | 18 | #N/A | #N/A | 290 | 1035 | 1035 | 290 | 280 | 40
18 | get into bath | 5 | 17 | 14 | 250 | 290 | 290 | 295 | 19 | #N/A | #N/A | 295 | 1035 | 1035 | 295 | 290 | 0
19 | wash body | 90 | 18 |  | 295 | 0 | 295 | 385 | 20 | #N/A | #N/A | 385 | 1035 | 1035 | 385 | 295 | 0
20 | shampoo hair | 40 | 19 |  | 385 | 0 | 385 | 425 | 21 | #N/A | #N/A | 425 | 1035 | 1035 | 425 | 385 | 0
21 | get dried | 30 | 20 |  | 425 | 0 | 425 | 455 | 22 | #N/A | #N/A | 455 | 1035 | 1035 | 455 | 425 | 0
22 | put on underwear | 10 | 21 |  | 455 | 0 | 455 | 465 | 23 | #N/A | #N/A | 465 | 1035 | 1035 | 465 | 455 | 0
23 | put on shirt and trousers | 30 | 22 |  | 465 | 0 | 465 | 495 | 24 | 25 | #N/A | 495 | 510 | 1035 | 495 | 465 | 0
24 | put on tie | 30 | 23 |  | 495 | 0 | 495 | 525 | 26 | #N/A | #N/A | 525 | 1035 | 1035 | 525 | 495 | 0
25 | walk to kitchen | 15 | 23 |  | 495 | 0 | 495 | 510 | #N/A | #N/A | 26 | 1035 | 1035 | 525 | 525 | 510 | 15
26 | lay table | 60 | 24 | 25 | 525 | 510 | 525 | 585 | 27 | #N/A | #N/A | 585 | 1035 | 1035 | 585 | 525 | 0
27 | make tea | 90 | 26 | 9 | 585 | 245 | 585 | 675 | 28 | 29 | #N/A | 675 | 735 | 1035 | 675 | 585 | 0
28 | spread toast | 60 | 27 | 11 | 675 | 235 | 675 | 735 | #N/A | #N/A | 29 | 1035 | 1035 | 735 | 735 | 675 | 0
29 | eat breakfast | 300 | 27 | 28 | 675 | 735 | 735 | 1035 | #N/A | #N/A | #N/A | 1035 | 1035 | 1035 | 1035 | 735 | 0
=MATCH(A29,D$1:D$40,FALSE) | [5 empty] | - find the row on which the activity is first cited as a dependancy, by looking down column D
=MATCH(A29,INDIRECT("D"&J29+1&":D40"),FALSE)+J29 | [5 empty] | - find the second citing by looking down the column below the first
=MATCH(A29,E$1:E$40,FALSE) | [5 empty] | - find the row on which the activity is first cited as a second dependancy, by looking down column E
=IF(ISERROR(J29),$I$29,INDIRECT("Q"&J29)) | [5 empty] | - the start of the first acitity which is dependant on this one, if there isn't one, return the end of the project
=MIN(M29:O29) | [5 empty] | - the stop is the earliest of the starts
=P29-C29 | [5 empty] | - the start of the activity is the stop minus the duration
=Q29-H29 | [5 empty] | - the Float is the difference between the Pull Start and the Push Start

## Section 40
Make-to-Stock (Inventory) Schedule
Up to now all our schedules have been make-to-order, and typically demand would come from sales orders or works orders. In traditional MRP logic, Master Production Scheduling (MPS) would be used to review finished inventory and sales forecasts, and generate manufacturing orders on the factory. The factory would then use the orders to create a schedule. In this example we use MPS and Finite Scheduling logic combined into one. The model is used to re-schedule quickly in response to changes in inventory levels.
There is one work centre that cycles through a portfolio of 5 products. If the rate of sales of any of the products, exceeds the rate of production, the logic will not work. The first job on the line is the one that is currently running, but after that the schedule decides four things:
- which product to make next
- the quantity to make
- when to stop
- how long to lie idle for
Each of these can be overridden by entering something in one of the three "Force" columns. Try this, and also change some of the values to see how the schedule responds.
Start of the first job: |  |  | 2000-03-14 08:00 | [5 empty] | A | B | C | D | E | A | B | C | D | E
Product running now: |  |  | C |  | Speed - units per hour |  |  |  | A: 300; B: 350; C: 280; D: 310; E: 240
Quantity committed: |  |  | 3400 |  | Forecast sales - units per week |  |  |  | A: 5000; B: 8000; C: 7000; D: 6500; E: 9000
[5 empty] | Min cover - days |  |  |  | A: 4; B: 4; C: 4; D: 4; E: 6
[5 empty] | Max cover - days |  |  |  | A: 14; B: 14; C: 14; D: 14; E: 14
[5 empty] | Min cover - units |  |  |  | A: 2857.1429; B: 4571.4286; C: 4000; D: 3714.2857; E: 7714.2857
[5 empty] | Max cover - units |  |  |  | A: 10000; B: 16000; C: 14000; D: 13000; E: 18000
Prod-uct | Force | Qty | Force | Idle hours | Force | Run hours | Start | Stop | A: Projected Inventory - units; A: Projected Cover - days | Lowest Cover | Offset | Next Prod | Inventory | Speed | For-cast | Min Cover | Min units | Max units | To make
[5 empty] | Opening stock: |  |  | 2000-03-14 08:00 | 10621 | 1566 | 8762 | 11984 | 12796 | 14.8694 | 1.3702 | 8.762 | 12.9058 | 9.9524
C |  | 3400 |  | 0 |  | 12.1429 | 2000-03-14 08:00 | 2000-03-14 20:09 | 10259.6054 | 987.7687 | 11656.0476 | 11514.1871 | 12145.4898 | 14.3634 | 0.8643 | 11.656 | 12.3999 | 9.4465 | 0.8643 | 2 | B | 987.7687 | 350 | 8000 | 4 | 4571.4286 | 16000 | 17376.3622
B |  | 17376.3622 |  | 0 |  | 49.6467 | 2000-03-14 20:09 | 2000-03-16 21:47 | 8782.0236 | 16000 | 9587.4331 | 9593.3307 | 9485.8425 | 12.2948 | 14 | 9.5874 | 10.3313 | 7.3779 | 7.3779 | 5 | E | 9485.8425 | 240 | 9000 | 6 | 7714.2857 | 18000 | 10960.7545
Idle |  | 0 |  | 33.0691 |  | 0 | 2000-03-16 21:47 | 2000-03-18 06:52 | 7797.8256 | 14425.2832 | 8209.5559 | 8313.8733 | 7714.2861 | 10.917 | 12.6221 | 8.2096 | 8.9534 | 6 | 6 | 5 | E | 7714.2861 | 240 | 9000 | 6 | 7714.2857 | 18000 | 13241.3788
E |  | 13241.3788 |  | 0 |  | 55.1724 | 2000-03-18 06:52 | 2000-03-20 14:02 | 6155.7896 | 11798.0255 | 5910.7054 | 6179.2264 | 18000 | 8.6181 | 10.3233 | 5.9107 | 6.6546 | 14 | 5.9107 | 3 | C | 5910.7054 | 280 | 7000 | 4 | 4000 | 14000 | 9503.507
Idle |  | 0 |  | 45.8569 |  | 0 | 2000-03-20 14:02 | 2000-03-22 11:53 | 4791.0001 | 9614.3623 | 4000.0001 | 4405.0001 | 15543.3789 | 6.7074 | 8.4126 | 4 | 4.7438 | 12.0893 | 4 | 3 | C | 4000.0001 | 280 | 7000 | 4 | 4000 | 14000 | 11748.2516
C |  | 11748.2516 |  | 0 |  | 41.958 | 2000-03-22 11:53 | 2000-03-24 05:51 | 3542.2488 | 7616.3603 | 14000 | 2781.6235 | 13295.6267 | 4.9591 | 6.6643 | 14 | 2.9956 | 10.341 | 2.9956 | 4 | D | 2781.6235 | 310 | 6500 | 4 | 3714.2857 | 13000 | 11675.5825
D |  | 11675.5825 |  | 0 |  | 37.6632 | 2000-03-24 05:51 | 2000-03-25 19:31 | 2421.3212 | 5822.8761 | 12430.7013 | 13000 | 11277.9569 | 3.3898 | 5.095 | 12.4307 | 14 | 8.7717 | 3.3898 | 1 | A | 2421.3212 | 300 | 5000 | 4 | 2857.1429 | 10000 | 8413.3351
A |  | 8413.3351 |  | 0 |  | 28.0445 | 2000-03-25 19:31 | 2000-03-26 23:33 | 10000 | 4487.4261 | 11262.1825 | 11914.9469 | 9775.5756 | 14 | 3.9265 | 11.2622 | 12.8315 | 7.6032 | 3.9265 | 2 | B | 4487.4261 | 350 | 8000 | 4 | 4571.4286 | 16000 | 13325.5777
B |  | 13325.5777 |  | 0 |  | 38.0731 | 2000-03-26 23:33 | 2000-03-28 13:38 | 8866.8726 | 16000 | 9675.8042 | 10441.8813 | 7735.9464 | 12.4136 | 14 | 9.6758 | 11.2451 | 6.0168 | 6.0168 | 5 | E | 7735.9464 | 240 | 9000 | 6 | 7714.2857 | 18000 | 13213.4943
Idle |  | 0 |  | 0.40433 |  | 0 | 2000-03-28 13:38 | 2000-03-28 14:02 | 8854.8391 | 15980.7464 | 9658.9573 | 10426.2377 | 7714.2861 | 12.3968 | 13.9832 | 9.659 | 11.2283 | 6 | 6 | 5 | E | 7714.2861 | 240 | 9000 | 6 | 7714.2857 | 18000 | 13241.3788
E |  | 13241.3788 |  | 0 |  | 55.1724 | 2000-03-28 14:02 | 2000-03-30 21:12 | 7212.8031 | 13353.4887 | 7360.1068 | 8291.5909 | 18000 | 10.0979 | 11.6843 | 7.3601 | 8.9294 | 14 | 7.3601 | 3 | C | 7360.1068 | 280 | 7000 | 4 | 4000 | 14000 | 7800.7137
Idle |  | 0 |  | 80.6426 |  | 0 | 2000-03-30 21:12 | 2000-04-03 05:51 | 4812.7266 | 9513.3663 | 3999.9997 | 5171.4914 | 13679.8623 | 6.7378 | 8.3242 | 4 | 5.5693 | 10.6399 | 4 | 3 | C | 3999.9997 | 280 | 7000 | 4 | 4000 | 14000 | 11748.2521
C |  | 11748.2521 |  | 0 |  | 41.958 | 2000-04-03 05:51 | 2000-04-04 23:48 | 3563.9753 | 7515.3642 | 14000 | 3548.1147 | 11432.11 | 4.9896 | 6.5759 | 14 | 3.821 | 8.8916 | 3.821 | 4 | D | 3548.1147 | 310 | 6500 | 4 | 3714.2857 | 13000 | 10799.7846
D |  | 10799.7846 |  | 0 |  | 34.838 | 2000-04-04 23:48 | 2000-04-06 10:39 | 2527.1296 | 5856.4111 | 12548.416 | 13000 | 9565.7878 | 3.538 | 5.1244 | 12.5484 | 14 | 7.4401 | 3.538 | 1 | A | 2527.1296 | 300 | 5000 | 4 | 2857.1429 | 10000 | 8295.8737
A |  | 8295.8737 |  | 0 |  | 27.6529 | 2000-04-06 10:39 | 2000-04-07 14:18 | 10000 | 4539.6058 | 11396.2114 | 11930.0956 | 8084.3817 | 14 | 3.9722 | 11.3962 | 12.8478 | 6.2879 | 3.9722 | 2 | B | 4539.6058 | 350 | 8000 | 4 | 4571.4286 | 16000 | 13265.1807
B |  | 13265.1807 |  | 0 |  | 37.9005 | 2000-04-07 14:18 | 2000-04-09 04:12 | 8872.0084 | 16000 | 9817.0232 | 10463.7066 | 6053.9969 | 12.4208 | 14 | 9.817 | 11.2686 | 4.7087 | 4.7087 | 5 | E | 6053.9969 | 240 | 9000 | 6 | 7714.2857 | 18000 | 15378.7626
E |  | 15378.7626 |  | 0 |  | 64.0782 | 2000-04-09 04:12 | 2000-04-11 20:16 | 6964.9198 | 12948.6582 | 7147.0991 | 7984.4914 | 18000 | 9.7509 | 11.3301 | 7.1471 | 8.5987 | 14 | 7.1471 | 3 | C | 7147.0991 | 280 | 7000 | 4 | 4000 | 14000 | 8050.9605
Idle |  | 0 |  | 75.5304 |  | 0 | 2000-04-11 20:16 | 2000-04-14 23:48 | 4716.9918 | 9351.9734 | 3999.9999 | 5062.185 | 13953.7296 | 6.6038 | 8.183 | 4 | 5.4516 | 10.8529 | 4 | 3 | C | 3999.9999 | 280 | 7000 | 4 | 4000 | 14000 | 11748.2518
C |  | 11748.2518 |  | 0 |  | 41.958 | 2000-04-14 23:48 | 2000-04-16 17:46 | 3468.2406 | 7353.9714 | 14000 | 3438.8084 | 11705.9773 | 4.8555 | 6.4347 | 14 | 3.7033 | 9.1046 | 3.7033 | 4 | D | 3438.8084 | 310 | 6500 | 4 | 3714.2857 | 13000 | 10924.6788
D |  | 10924.6788 |  | 0 |  | 35.2409 | 2000-04-16 17:46 | 2000-04-18 05:00 | 2419.4043 | 5675.8333 | 12531.6292 | 13000 | 9818.072 | 3.3872 | 4.9664 | 12.5316 | 14 | 7.6363 | 3.3872 | 1 | A | 2419.4043 | 300 | 5000 | 4 | 2857.1429 | 10000 | 8415.4631
A |  | 8415.4631 |  | 0 |  | 28.0515 | 2000-04-18 05:00 | 2000-04-19 09:03 | 10000 | 4340.0456 | 11362.8149 | 11914.6724 | 8315.3108 | 14 | 3.7975 | 11.3628 | 12.8312 | 6.4675 | 3.7975 | 2 | B | 4340.0456 | 350 | 8000 | 4 | 4571.4286 | 16000 | 13496.1677
B |  | 13496.1677 |  | 0 |  | 38.5605 | 2000-04-19 09:03 | 2000-04-20 23:37 | 8852.3667 | 16000 | 9756.1282 | 10422.7491 | 6249.5708 | 12.3933 | 14 | 9.7561 | 11.2245 | 4.8608 | 4.8608 | 5 | E | 6249.5708 | 240 | 9000 | 6 | 7714.2857 | 18000 | 15126.9893
E |  | 15126.9893 |  | 0 |  | 63.0291 | 2000-04-20 23:37 | 2000-04-23 14:39 | 6976.5 | 12998.6132 | 7129.9148 | 7984.1224 | 18000 | 9.7671 | 11.3738 | 7.1299 | 8.5983 | 14 | 7.1299 | 3 | C | 7129.9148 | 280 | 7000 | 4 | 4000 | 14000 | 8071.149
Idle |  | 0 |  | 75.118 |  | 0 | 2000-04-23 14:39 | 2000-04-26 17:46 | 4740.8465 | 9421.5676 | 3999.9999 | 5077.7728 | 13975.8237 | 6.6372 | 8.2439 | 4 | 5.4684 | 10.8701 | 4 | 3 | C | 3999.9999 | 280 | 7000 | 4 | 4000 | 14000 | 11748.2518
Formulas:
Stop = [Start]+(([Run hours]+[Idle hours])/24)
Start = [Stop, row above]

## Section 41
Make-to-Stock Logic Explained
The logic works as follows:
- | the first job is the "Product running now"
| - | it starts at the "Start of the first job"
| - | and the "Quantity committed" is specified
- | the duration of the job is calculated from the speed, and shown in the "Run hours" column
- | a separate column for each product records the projected inventory level at the end of each job
- | at the end of each job, the inventory level of one product has risen, and the other four products have fallen
- | the opening inventory is recorded at the top of the columns, and would typically come from an inventory management system
- | the inventory at the end of the job is the opening inventory, less the forecast sales for the duration of the job, plus the production quantity of the job
- | another bank of five columns expresses the projected inventory level as days of cover
- | the product with the lowest cover at the end of the job is identified as the next product to be made
- | the quantity to make is that required to increase the inventory level to the maximum, plus sufficient to replenish the amount sold while the job was running
- | the duration of the next job is calculated, and the cycle begins again
- | if the projected inventory level of the lowest cover product is above its minimum, then an idle period is scheduled
- | the duration of the idle period is the time it will take for forecast sales to reduce the inventory to the minimum and trigger the next run
You will see from the chart of inventory cover, that the model attempts to keep the inventory of each product between the minimum and maximum.

## Section 42
Make-to-Stock Schedule - Formulas Explained
Start of the first job: |  |  | 2000-03-14 08:00 | [5 empty] | A | B | C | D | E | A | B | C | D | E
Product running now: |  |  | C |  | Speed - units per hour |  |  |  | A: 300; B: 350; C: 280; D: 310; E: 240
Quantity committed: |  |  | 3400 |  | Forecast sales - units per week |  |  |  | A: 5000; B: 8000; C: 7000; D: 6500; E: 9000
[5 empty] | Min cover - days |  |  |  | A: 4; B: 4; C: 4; D: 4; E: 6
[5 empty] | Max cover - days |  |  |  | A: 14; B: 14; C: 14; D: 14; E: 14
[5 empty] | Min cover - units |  |  |  | A: 2857.1429; B: 4571.4286; C: 4000; D: 3714.2857; E: 7714.2857
[5 empty] | Max cover - units |  |  |  | A: 10000; B: 16000; C: 14000; D: 13000; E: 18000
Prod-uct | Force | Qty | Force | Idle hours | Force | Run hours | Start | Stop | A: Projected Inventory - units; A: Projected Cover - days | Lowest Cover | Offset | Next Prod | Inventory | Speed | For-cast | Min Cover | Min units | Max units | To make
[5 empty] | Opening stock: |  |  | 2000-03-14 08:00 | 10621 | 1566 | 8762 | 11984 | 12796 | 14.8694 | 1.3702 | 8.762 | 12.9058 | 9.9524
C |  | 3400 |  | 0 |  | 12.1429 | 2000-03-14 08:00 | 2000-03-14 20:09 | 10259.6054 | 987.7687 | 11656.0476 | 11514.1871 | 12145.4898 | 14.3634 | 0.8643 | 11.656 | 12.3999 | 9.4465 | 0.8643 | 2 | B | 987.7687 | 350 | 8000 | 4 | 4571.4286 | 16000 | 17376.3622
B |  | 17376.3622 |  | 0 |  | 49.6467 | 2000-03-14 20:09 | 2000-03-16 21:47 | 8782.0236 | 16000 | 9587.4331 | 9593.3307 | 9485.8425 | 12.2948 | 14 | 9.5874 | 10.3313 | 7.3779 | 7.3779 | 5 | E | 9485.8425 | 240 | 9000 | 6 | 7714.2857 | 18000 | 10960.7545
Idle |  | 0 |  | 33.0691 |  | 0 | 2000-03-16 21:47 | 2000-03-18 06:52 | 7797.8256 | 14425.2832 | 8209.5559 | 8313.8733 | 7714.2861 | 10.917 | 12.6221 | 8.2096 | 8.9534 | 6 | 6 | 5 | E | 7714.2861 | 240 | 9000 | 6 | 7714.2857 | 18000 | 13241.3788
E |  | 13241.3788 |  | 0 |  | 55.1724 | 2000-03-18 06:52 | 2000-03-20 14:02 | 6155.7896 | 11798.0255 | 5910.7054 | 6179.2264 | 18000 | 8.6181 | 10.3233 | 5.9107 | 6.6546 | 14 | 5.9107 | 3 | C | 5910.7054 | 280 | 7000 | 4 | 4000 | 14000 | 9503.507
Idle |  | 0 |  | 45.8569 |  | 0 | 2000-03-20 14:02 | 2000-03-22 11:53 | 4791.0001 | 9614.3623 | 4000.0001 | 4405.0001 | 15543.3789 | 6.7074 | 8.4126 | 4 | 4.7438 | 12.0893 | 4 | 3 | C | 4000.0001 | 280 | 7000 | 4 | 4000 | 14000 | 11748.2516
A | Product |  |  |  | =IF(E19,"Idle",IF(ISBLANK(A18),D$6,IF(ISBLANK(B19),V18,B19))) |  |  |  | A: if there are idle hours return "Idle", else, if it’s the first job return Job now running, else, if force is blank return next product from previous row, else forced value
C | Qty |  |  |  | =IF(A19="Idle",0,IF(ISBLANK(C18),D$7,IF(ISBLANK(D19),AC18,D19))) |  |  |  | A: if its an idle period put zero, else if it’s the first job return quantity committed, else forced value if there is one, else to make
E | Idle hours |  |  |  | =MAX(IF(ISBLANK(F19),IF(Y18,ROUND((W18-AA18)/Y18,7),0)*168,F19),0) |  |  |  | A: return the force value if there is one, else no of weeks for stock to reach minimum, times 168 for hours, but 0 if its -ve
G | Run hours |  |  |  | =C19/HLOOKUP(A19,$J$5:$N$9,2) |  |  |  | A: quantity divided by the speed for that product, looked up in the horizontal table
H | Start |  |  |  | =I18 |  |  |  | A: stop of the previous job
I | Stop |  |  |  | =H19+((G19+E19)/24) |  |  |  | A: start plus idle hours plus run hours, divided by 24 to get to days
J | Projected Inventory - units |  |  |  | =J18-(J$7*($G19+$E19)/168)+(($A19=J$5)*$C19) |  |  |  | A: Inventory at the end of the previous job, less forecast sales for the duration of the job, plus qty if the job is for the product
O | Projected Cover - days |  |  |  | =J19/J$7*7 |  |  |  | A: inventory divided by forecast
T | Lowest Cover |  |  |  | =MIN(O19:S19) |  |  |  | A: lowest inventory cover at the end of the job
U | Offset |  |  |  | =MATCH(T19,O19:S19,0) |  |  |  | A: find the offset of the product with the lowest inventory cover
V | Next Prod |  |  |  | =INDEX(O$5:S$5,1,U19) |  |  |  | A: for the product, get the:; E: product code
W | Inventory |  |  |  | =INDEX(J19:N19,1,U19) |  |  |  | E: inventory level
X | Speed |  |  |  | =INDEX(J$6:N$6,1,U19) |  |  |  | E: speed
Y | Forecast |  |  |  | =INDEX(J$7:N$7,1,U19) |  |  |  | E: forecast sales per week
Z | Min Cover |  |  |  | =INDEX(J$8:N$8,1,U19) |  |  |  | E: minimum inventory cover in days
AA | Min units |  |  |  | =INDEX(J$10:N$10,1,U19) |  |  |  | E: minimum inventory in units
AB | Max units |  |  |  | =INDEX(J$11:N$11,1,U19) |  |  |  | E: maximum inventory in units
AC | To make |  |  |  | =AB19-W19+Y19*(AB19-W19)/(X19-Y19/168)/168 |  |  |  | A: this formula has been created by substituting together the following:
AE | Inventory replenishment qty |  |  |  | =AB19-W19 |  |  |  | A: maximum inventory minus inventory level
AF | forecast units per hour |  |  |  | =Y19/168 |  |  |  | A: sales forecast in units per week, divided by 168 (7x24), to get to units per hour
AG | effective speed |  |  |  | =X19-AF19 |  |  |  | A: speed of building inventory, rate of production minus rate of sales
AH | run duration |  |  |  | =AE19/AG19 |  |  |  | A: time it will take to build up the replenishment quantity
AI | sales during production |  |  |  | =AH19*AF19 |  |  |  | A: units that will be sold while the job is running
| to make |  |  |  | =AE19+AI19 |  |  |  | A: Inventory replenishment qty plus sales during production
Formulas:
Stop = [Start]+(([Run hours]+[Idle hours])/24)
Start = [Stop, row above]

## Section 43
Inventory Cover Calculation
In Section 40 the sales forecast is expressed as a straight line, e.g.. 100 units per week. Calculating the inventory cover is a simple division, e.g.. an inventory of 650 will last for 6.5 weeks. However, a sales forecast may be non-linear, to reflect seasonal sales demand, sales promotions, a new product with an anticipated increase in demand, or a product at the end of it's life cycle. Calculating the cover with a non-linear forecast, is more complex. Here is a sales forecast for 20 weeks which falls and then rises again:
Weeks |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
Sales forecast: |  | 80 | 76 | 72 | 68 | 64 | 60 | 56 | 52 | 48 | 44 | 40 | 40 | 44 | 48 | 52 | 56 | 60 | 64 | 68 | 72
Cum forecast: | 0 | 80 | 156 | 228 | 296 | 360 | 420 | 476 | 528 | 576 | 620 | 660 | 700 | 744 | 792 | 844 | 900 | 960 | 1024 | 1092 | 1164
Here is an inventory cover calculation:
Inventory: |  | 7: 500
the week in which the inventory will run out |  | 7: 8; 9: =MATCH(I13,B9:Z9)
cumulative forecast at the end of the previous week |  | 7: 476; 9: =INDEX(B9:Z9,1,I14)
inventory left in the last week |  | 7: 24; 9: =I13-I15
forecast for the last week |  | 7: 52; 9: =INDEX(C7:Z7,1,I14)
portion of the week that the inventory will last |  | 7: 0.46154; 9: =I16/I17
cover - weeks that the inventory will last |  | 7: 7.4615; 9: =I14-1+I18
What if the inventory cover is greater then 20 weeks? We could assume that the forecast for the 20th week will continue in a straight line at 72 per week thereafter. Here are some additional steps to cope with that:
Inventory: |  | 7: 2000
last week |  | 7: 20; 9: =MAX(C5:Z5)
last forecast quantity |  | 7: 72; 9: =INDEX(C7:Z7,1,I24)
last cum forecast |  | 7: 1164; 9: =MAX(C9:Z9)
cover after the last week |  | 7: 11.6111; 9: =(I23-I26)/I25
total cover |  | 7: 31.6111; 9: =I24+I27
test to see if this should be applied |  | 7: 1; 9: =I23>I26
Now lets consider a forecast that drops away to zero, and inventory which will last for infinity. Speadsheets don't return a value for infinity, they return an error, so lets adopt a convention that infinite cover is represented by the value 999.
Sales forecast: |  | 80 | 75 | 70 | 65 | 60 | 55 | 50 | 45 | 40 | 35 | 30 | 25 | 20 | 15 | 10 | 5 | 0 | 0 | 0 | 0
Cum forecast: | 0 | 80 | 155 | 225 | 290 | 350 | 405 | 455 | 500 | 540 | 575 | 605 | 630 | 650 | 665 | 675 | 680 | 680 | 680 | 680 | 680
Inventory: |  | 7: 2000
last week |  | 7: 20
last forecast quantity |  | 7: 0
last cum forecast |  | 7: 680
cover after the last week |  | 7: #DIV/0!
total cover |  | 7: 999; 9: =IF(I39,I38+I41,999)
The whole lot can be substituted together as follows:
the week in which the inventory will run out |  | 7: 8
total cover |  | 7: 7.4615
=IF(I13>MAX(C9:Z9),IF(INDEX(C7:Z7,1,MAX(C5:Z5)),MAX(C5:Z5)+(I13-MAX(C9:Z9))/INDEX(C7:Z7,1,MAX(C5:Z5)),999),
I46-1+(I13-INDEX(B9:Z9,1,I46))/INDEX(C7:Z7,1,I46))